## AI Assumptions
AI Acceleration Factors - How Traditional vs AI Days Are Calculated
Yellow cells = user-adjustable inputs ¦ Blue cells = auto-calculated formulas
Section A: AI Acceleration Multipliers by Activity Type
Activity Category | AI Acceleration Factor | Explanation / How AI Reduces Time | Traditional Effort Driver | AI Approach | Residual Manual %
Infrastructure Discovery | 28% | 72% savings (Industry std: 65%). CloudMigrate unified multi-cloud scan adds +7% over separate tools by eliminating 3-5 days of cross-cloud reconciliation for 4273 servers. [Ref: Gartner 2024 + CloudMigrate benchmark] | Manual server-by-server inventory, spreadsheet reconciliation, app owner interviews | vCenter/AD/SCCM API scan + CMDB correlation; manual reconciliation still needed for legacy, air-gapped, undocumented systems | 35%
App Dependency Mapping | 35% | 65% savings (Industry std: 60%). CloudMigrate AI graph builder catches cross-app patterns that individual tools miss, reduces manual interview rounds from 3 to 1. [Ref: Gartner 2024 + CloudMigrate benchmark] | Manual interviews with app owners, network trace analysis, cross-team dependency workshops | Network flow analysis + port mapping + AI graph; manual validation workshops still critical for accuracy | 40%
Database Analysis | 30% | 70% savings (Industry std: 65%). CloudMigrate DB Remediation Engine adds AI-suggested fixes beyond SCT reporting, saving DBA manual effort on repetitive patterns. [Ref: AWS SCT docs + CloudMigrate DB engine benchmark] | Manual schema review, stored proc analysis, compatibility matrix building | AWS SCT/Azure DMA automated scan + compatibility report; manual review for complex PL/SQL, T-SQL objects | 35%
Performance Baseline | 30% | 70% savings. Metric collection is fully automated via APIs, but baseline analysis, anomaly identification, and threshold setting require human judgment. [Ref: AWS CloudWatch + custom baselining] | Manual metric collection, spreadsheet charting, baseline documentation, anomaly identification | API-driven metric aggregation + statistical baseline computation; human review for threshold decisions | 30%
Compliance & Security | 48% | 52% savings (Industry std: 50%). CloudMigrate MCP compliance-framework provides structured gap reporting; marginal +2% — NERC CIP evidence collection remains manual-heavy. [Ref: NERC CIP + CloudMigrate compliance service] | Manual control review, evidence collection, policy mapping, regulatory documentation | Automated compliance scanning + gap detection; manual evidence collection, NERC CIP sign-off mandatory | 50%
License Analysis | 40% | 60% savings. CMDB-driven license scanning identifies ~60-70% of license entitlements, but vendor contract interpretation, BYOL eligibility negotiation remain manual. [Ref: Flexera State of IT 2024] | Manual license inventory, vendor contract review, BYOL eligibility assessment | CMDB-driven license scan + cloud pricing correlation; vendor contract review still manual | 40%
TCO / Cost Modeling | 25% | 75% savings (Industry std: 70%). CloudMigrate MCP cloud-cost service generates unified multi-cloud TCO auto-linked to actual discovered inventory vs manual calculator input. [Ref: AWS Pricing + Cobalt benchmarks] | Manual spreadsheet modeling, vendor quote gathering, assumption documentation | Auto-generated TCO from discovery + live cloud pricing APIs; manual for EDP/RI assumptions, stakeholder review | 30%
Wave Planning | 35% | 65% savings (Industry std: 60%). CloudMigrate graph-based wave optimizer with parallel simulation generates optimal wave plans faster than manual spreadsheet analysis. [Ref: McKinsey 2023 + CloudMigrate wave planner] | Manual dependency review, stakeholder negotiation, change window scheduling | Graph-based optimization + risk-weighted scheduling; stakeholder alignment and change windows manual | 40%
Landing Zone Design | 35% | 65% savings (validation only since PG&E provides LZ). Template-based validation fast, but custom PG&E requirements need manual gap analysis. [Ref: AWS Landing Zone Accelerator] | Manual architecture review, compliance gap analysis, design documentation | Template-based validation + automated readiness check; manual for PG&E-specific customizations | 35%
Terraform/IaC Generation | 25% | 75% savings (Industry std: 70%). CloudMigrate MCP terraform-gen auto-populates HCL from discovery data, eliminating manual inventory-to-variable translation. [Ref: HashiCorp 2024 + CloudMigrate terraform-gen] | Manual HCL writing, module development, testing, review iterations | Auto-generated Terraform from discovery + template library; manual for module customization, PR review | 30%
Container Artifact Gen | 35% | 65% savings (Industry std: 60%). CloudMigrate AI source-code analysis generates stack-aware Dockerfiles+K8s manifests, catching runtime dependencies generic tools miss. [Ref: CNCF 2024 + CloudMigrate container engine] | Manual Dockerfile creation, K8s manifest writing, Helm chart development | Source code analysis + Dockerfile/manifest auto-gen; manual for custom configs, runtime dependencies | 40%
Framework Upgrades | 53% | 47% savings (Industry std: 45%). CloudMigrate Upgrade Advisor adds migration-context-aware breaking change detection; code changes still largely manual. [Ref: GitHub Copilot + CloudMigrate upgrade advisor] | Manual code refactoring, dependency updates, regression fixing, build testing | AI-identified upgrade paths + breaking change detection; code changes semi-manual with AI assist | 55%
Middleware Migration | 53% | 47% savings (Industry std: 45%). CloudMigrate config extractor provides partial automation; custom plugins and job scheduling logic remain manual. [Ref: Industry avg + CloudMigrate config extractor] | Manual config extraction, version migration, plugin compatibility testing | Config extraction + partial automation; manual for custom plugins, job scheduling logic | 55%
Schema Conversion | 35% | 65% savings (Industry std: 60%). CloudMigrate DB Remediation Engine provides AI pattern matching for common PL/SQL-to-PostgreSQL transforms beyond SCT. [Ref: AWS SCT tiers + CloudMigrate DB remediation] | Manual stored proc rewriting, trigger conversion, cross-DB reference resolution | SCT auto-conversion (60-80% simple objects) + AI-assisted fix; manual for complex PL/SQL/T-SQL | 40%
Rehearsal / Dry Run | 40% | 60% savings (Industry std: 55%). CloudMigrate orchestrated rehearsal + automated outcome validation saves 1-2 days per wave vs manual runbook execution. [Ref: AWS Playbook + CloudMigrate rehearsal engine] | Manual rehearsal execution, validation checklist, defect logging, re-planning | Orchestrated rehearsal + automated outcome validation; manual triage and re-planning from findings | 45%
Rehost Execution | 37% | 63% savings (Industry std: 60%). CloudMigrate unified execution pipeline orchestrates MGN/ASR + cutover + DNS + validation, reducing handoff time. [Ref: AWS MGN + Gartner + CloudMigrate executor] | Manual server migration, replication monitoring, cutover coordination, post-migration validation | AWS MGN/Azure ASR automated replication + cutover scheduling; manual for validation and rollback decisions | 40%
Replatform Execution | 43% | 57% savings (Industry std: 55%). CloudMigrate auto-generates pre/post validation checks from discovery baselines, saving manual checklist creation. [Ref: Industry avg + CloudMigrate executor] | Manual OS patching, DB upgrade, compatibility testing, validation | Scripted OS/DB upgrades + automated pre/post validation; manual compatibility testing and sign-off | 45%
Containerize Execution | 42% | 58% savings (Industry std: 55%). CloudMigrate pre-configured CI/CD from artifact gen phase eliminates manual pipeline setup; health checks auto-generated. [Ref: CNCF 2024 + CloudMigrate CI/CD] | Manual Docker build, push, K8s deploy, smoke test, config tuning | CI/CD pipeline build+push+deploy + automated health checks; manual smoke testing and config tuning | 45%
FR Testing (60%) | 47% | 53% savings (Industry std: 50%). CloudMigrate AI test generator creates test cases from app behavior analysis, saving ~20-30% of test design time. [Ref: Forrester TEI + CloudMigrate test generator] | Manual test case design, execution, defect logging, root cause analysis | AI test generation + parallel automated execution; manual test design for business logic, defect triage | 50%
NFR Testing (30%) | 48% | 52% savings (Industry std: 50%). CloudMigrate auto-generates load scripts from real traffic patterns — more representative than manually designed scenarios. [Ref: Gartner + CloudMigrate perf test gen] | Manual JMeter/Gatling scripting, scenario design, result analysis, bottleneck identification | Auto-generated load scripts from traffic patterns + AI performance analysis; manual scenario design | 50%
Right-Sizing | 28% | 72% savings (Industry std: 70%). CloudMigrate unified cross-cloud right-sizing adds comparison view; cloud-native tools already excellent individually. [Ref: AWS Compute Optimizer + CloudMigrate right-sizing] | Manual CloudWatch analysis, sizing spreadsheets, vendor benchmarking | ML-based 30-day usage analysis + automated SKU recommendation; human review for business constraints | 30%
Monitoring Setup | 43% | 57% savings (Industry std: 55%). CloudMigrate pre-built templates auto-deployed from discovery metadata; alert thresholds auto-suggested from baselines. [Ref: Datadog/Grafana + CloudMigrate monitoring templates] | Manual dashboard creation, alert configuration, SLO definition, escalation setup | Template deployment + standard alert rules; manual for PG&E-specific SLOs and escalation policies | 45%
Vuln Discovery Scan | 32% | 68% savings (Industry std: 65%). CloudMigrate migration-context-aware CVSS triage deprioritizes CVEs on servers being retired, prioritizes migrate-first targets. [Ref: Tenable/Qualys + CloudMigrate vuln scanner] | Manual scan scheduling, CSV export, CVSS triage, false positive validation | Automated scan orchestration + CVSS auto-categorization + false-positive filtering; manual for context-specific risk assessment | 35%
Vuln Remediation Planning | 42% | 58% savings (Industry std: 55%). CloudMigrate migration-aware scheduling prevents patch-migrate conflicts; auto-generated runbooks save 1-2 days per wave. [Ref: ServiceNow VR + CloudMigrate vuln planner] | Manual CVE-to-patch mapping, dependency analysis, change request creation, CAB scheduling | AI-prioritized remediation plan + auto-generated runbooks; manual for dependency analysis and CAB approval | 45%
Vuln Patch Execution | 43% | 57% savings (Industry std: 55%). CloudMigrate orchestrated patching with auto-generated NERC CIP compliance evidence trail. [Ref: AWS SSM + CloudMigrate patch executor] | Manual patch deployment, snapshot creation, reboot coordination, compliance evidence | SSM/Ansible automated patching + post-patch validation; manual for snapshots, rollback testing, NERC CIP evidence | 45%
Vuln Continuous Monitoring | 38% | 62% savings (Industry std: 60%). CloudMigrate continuous scanning + auto-ticketing + Grafana vuln posture dashboard with SLA tracking. [Ref: Industry avg + CloudMigrate vuln monitor] | Periodic manual scans, spreadsheet tracking, manual ticket creation, SLA monitoring | Continuous scanning + auto-ticketing for new CVEs + SLA dashboards; manual for follow-up and exec reporting | 40%
Section B: Scale Factors (Server/App Volume Impact on Duration)
Factor | Value | Description
Total Applications | 415 | From PG&E landscape analysis
Total Servers | 4273 | Across all platforms
AWS Apps | 107 | Target platform count
Azure Apps | 145 | Target platform count
Azure Local Apps | 110 | Target platform count
HyperV Apps | 20 | Target platform count
Containerize Apps | 159 | Journey type count
Lift-and-Shift Apps | 179 | Journey type count
Retire Apps | 24 | Journey type count
Base Days per Discovery (per 100 servers) | 5 | Industry benchmark: 5 days per 100 servers manual
Base Days per App (Dependency Map) | 0.3 | Industry benchmark: ~0.3 days per app manual
Base Days per App (Wave Planning) | 0.2 | Industry benchmark: ~0.2 days per app manual
Base Days per App (Rehost Execution) | 0.5 | Industry benchmark: ~0.5 days per app manual
Base Days per App (Containerize) | 1.2 | Industry benchmark: ~1.2 days per app manual
Section C: How Duration Is Calculated (Formula Methodology)
TRADITIONAL DAYS = Base Days per unit x Volume (apps or servers) x Complexity multiplier
Example: Infrastructure Discovery = (4273 servers / 100) x 5 base days = ~214 person-days, split across 3 clouds
Example: App Dependency Mapping = 415 apps x 0.3 days/app = ~125 person-days, split across 3 clouds
AI-ACCELERATED DAYS = Traditional Days x AI Acceleration Factor (from Section A)
Example: Discovery Traditional=20 days (AWS share), AI Factor=20% => AI Days = 20 x 0.20 = 4 days
Example: Containerize Trad=25 days, AI Factor=20% => AI Days = 25 x 0.20 = 5 days
TIME SAVED % = (Traditional - AI) / Traditional x 100
Example: (20 - 4) / 20 x 100 = 80% time saved on discovery
KEY PRINCIPLES (Industry-Validated):
1. Discovery & data-heavy activities: 60-70% savings (Gartner 2024: discovery tools reduce effort 50-70%)
2. IaC / code generation: 60-70% savings (HashiCorp: IaC reduces provisioning 60-75%)
3. Execution (Rehost/Replatform): 55-60% savings (AWS MGN automates replication, cutover manual)
4. Code-change activities (Framework, Middleware): 45% savings (GitHub Copilot: 30-50% faster)
5. Testing (FR/NFR): 50% savings (Forrester: test automation reduces execution 40-60%)
6. Compliance/NERC CIP: 50% savings (regulatory evidence collection still manual-heavy)
7. Vulnerability Management: 55-65% savings (scanning automated, triage/patching semi-manual)
OVERALL BLENDED SAVINGS: ~62% with CloudMigrate.store (Industry std: ~59% ¦ McKinsey benchmark: 40-60%)
CloudMigrate premium: +3% over industry standard from unified multi-cloud integration & pipeline automation
INDUSTRY REFERENCES:
- McKinsey (2023): AI accelerates cloud migration by 30-50% overall
- Gartner Magic Quadrant Migration Tools (2024): 50-70% for discovery, 45-65% for execution
- AWS Well-Architected Migration Lens: MGN replication automated, cutover manual
- Forrester TEI: Migration platforms show 40-60% efficiency gains
- Infosys Cobalt benchmarks: 30-40% acceleration on traditional, 50-65% with AI augmentation
- AWS SCT: Auto-conversion rate 60-80% depending on DB complexity tier
- HashiCorp State of Cloud (2024): IaC reduces provisioning time 60-75%
- CNCF Survey (2024): Containerization deployment 50-60% automatable
ADJUST: Change yellow cells in Section A to model scenarios:
Conservative: Set all factors to 0.55-0.60 (40-45% savings) - defensible for skeptical stakeholders
Moderate: Current values (45-70% savings) - industry-aligned, realistic for AI-augmented migration
Aggressive: Set data-processing factors to 0.20-0.25 (75-80% savings) - requires mature tooling + experienced team

## Migration Activities
PG&E Cloud Migration - Activities, Duration & AI Accelerator Savings
415 Apps ¦ 4,273 Servers ¦ All durations formula-driven from AI Assumptions tab (yellow = input, blue = formula)
CIS CLD (AWS/Azure) ¦ CIS EIT (Azure Local/HyperV) ¦ ADM (Containerize/Framework) ¦ IQE (Testing) ¦ CyberSec (Security)
Phase | Activity | Team | Description | AWS Trad (Days) | AWS AI (Days) | AWS Saved % | Azure Trad (Days) | Azure AI (Days) | Azure Saved % | AzLocal/HV Trad (Days) | AzLocal/HV AI (Days) | AzLocal/HV Saved % | CloudMigrate.store Accelerator Activity | AI Factor Ref | How Calculated
Phase 1: Discovery & Assessment [COMPLETED]
| Infrastructure Discovery (4273 servers) [DONE] | CIS CLD + EIT | COMPLETED - All VMs, physical, DBs, network discovered | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Auto-Discovery Engine: vCenter/AD/SCCM scan, 29 component types detected, topology mapping | Infrastructure Discovery | COMPLETED - Phase 1 done
| App Dependency Mapping (415 apps) [DONE] | CIS CLD + ADM | COMPLETED - All 415 app dependencies mapped | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Dependency Mapper: Network flow tracing, port analysis, CMDB correlation, dependency graph generation | App Dependency Mapping | COMPLETED - Phase 1 done
| Database Schema Analysis [DONE] | CIS CLD | COMPLETED - Schemas, stored procs analyzed | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | DB Analysis Agent: Schema compatibility scan, stored proc analysis, managed DB target recommendation | Database Analysis | COMPLETED - Phase 1 done
| Performance Baseline [DONE] | CIS CLD + EIT | COMPLETED - CPU, mem, IOPS baselines captured | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Perf Baseline Agent: Automated metric aggregation, statistical baseline computation, anomaly detection | Performance Baseline | COMPLETED - Phase 1 done
| Compliance & Security Audit [DONE] | CyberSec | COMPLETED - PG&E NERC CIP compliance reviewed | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Compliance Scanner: MCP compliance-framework service, NERC CIP gap detection, remediation recommendations | Compliance & Security | COMPLETED - Phase 1 done
| License Analysis (BYOL) [DONE] | CIS CLD | COMPLETED - Oracle, SQL Server, SAP licenses audited | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | License Analyzer: CMDB license correlation, BYOL eligibility check, cloud pricing comparison | License Analysis | COMPLETED - Phase 1 done
| TCO / Cost Modeling [DONE] | CIS CLD | COMPLETED - TCO built for each target platform | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Cost Modeling Engine: MCP cloud-cost service, auto-TCO from discovery, multi-cloud comparison | TCO / Cost Modeling | COMPLETED - Phase 1 done
| Journey Assignment & 6R [DONE] | CIS CLD + ADM | COMPLETED - 415 apps classified into journeys | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Strategy Agent: AI 6R classification, journey recommendation per app profile, complexity scoring | Wave Planning | COMPLETED - Phase 1 done
| Vulnerability Baseline Scan [DONE] | CyberSec | COMPLETED - 4273 servers scanned, CVSS categorized | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Vuln Scanner: Automated Nessus/Qualys orchestration, CVSS auto-triage, false-positive filtering, risk heatmap | Vuln Discovery Scan | COMPLETED - Phase 1 done
| Vuln Remediation Plan [DONE] | CyberSec | COMPLETED - Critical/high CVEs prioritized for remediation | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Vuln Remediation Planner: AI-prioritized patch plan, runbook generation, change request drafts | Vuln Remediation Planning | COMPLETED - Phase 1 done
Phase 2: Planning & Design
| Wave Planning (7 waves) | CIS CLD | Group 415 apps into 7 waves | 12 |  |  | 12 |  |  | 12 |  |  | Wave Planner: Dependency-graph optimization, risk-weighted scheduling, parallel wave simulation | Wave Planning | 415 apps x 0.2d = 83 total, graph optimization
| LZ Validation - AWS (PG&E Provided) | CIS CLD | Validate PG&E-built VPC/subnets/SG/IAM | 3 |  |  | 0 | 0 |  | 0 | 0 |  | LZ Validator: Automated readiness check against migration requirements, gap report | Landing Zone Design | PG&E provides LZ; Infosys validates readiness
| LZ Validation - Azure (PG&E Provided) | CIS CLD | Validate PG&E-built VNet/NSG/RBAC | 0 | 0 |  | 3 |  |  | 0 | 0 |  | LZ Validator: Automated readiness check against migration requirements, gap report | Landing Zone Design | PG&E provides LZ; Infosys validates readiness
| LZ Validation - AzLocal/HV (PG&E Provided) | CIS EIT | Validate PG&E-built Azure Local/HyperV | 0 | 0 |  | 0 | 0 |  | 5 |  |  | LZ Validator: Cluster config validation, capacity check for workload placement | Landing Zone Design | PG&E provides infra; EIT validates config
| App-Level IaC Generation | CIS CLD + EIT | Generate app-level Terraform (SG, LB, DNS) | 10 |  |  | 10 |  |  | 12 |  |  | Terraform Generator: MCP terraform-gen service, app-level HCL from discovery, PR-ready output | Terraform/IaC Generation | App-level only; foundational IaC by PG&E
| DB Migration Planning (DMS/DMA) | CIS CLD | Schema conversion, CDC strategy | 10 |  |  | 10 |  |  | 12 |  |  | DB Migration Planner: DMS task design, CDC strategy recommendation, cutover window calculation | Database Analysis | DMS task planning per DB target
| Containerization Architecture | ADM | Docker/K8s design for 159 apps | 15 |  |  | 15 |  |  | 15 |  |  | Container Architect Agent: Source code analysis, Docker/K8s architecture recommendation, manifest templates | Container Artifact Gen | 159 containerize apps, arch design
| Rollback & DR Strategy | CIS CLD | Rollback procedures per wave, DR plan | 8 |  |  | 8 |  |  | 8 |  |  | Rollback Planner: Auto-generated rollback scripts per wave, DR validation checklist | Compliance & Security | Template-based + manual review
| Business Impact Assessment | CIS CLD | Downtime cost per app tier | 5 |  |  | 5 |  |  | 5 |  |  | Business Impact Engine: Downtime cost calculator, user impact modeling, ROI projection | TCO / Cost Modeling | AI computes from app metadata
Phase 3: Build & Prepare
| App-Level Provisioning - AWS | CIS CLD | Deploy app SGs, target groups, DNS in PG&E LZ | 5 |  |  | 0 | 0 |  | 0 | 0 |  | Executor: terraform apply for app-level resources in PG&E-provided LZ | Terraform/IaC Generation | PG&E LZ ready; app-level config only
| App-Level Provisioning - Azure | CIS CLD | Deploy app NSGs, LB rules, DNS in PG&E LZ | 0 | 0 |  | 5 |  |  | 0 | 0 |  | Executor: terraform apply for app-level resources in PG&E-provided LZ | Terraform/IaC Generation | PG&E LZ ready; app-level config only
| Workload Onboarding - AzLocal/HV | CIS EIT | Onboard workloads to PG&E-built clusters | 0 | 0 |  | 0 | 0 |  | 10 |  |  | Onboarding Orchestrator: Workload placement optimization on PG&E clusters | Middleware Migration | PG&E provides infra; EIT onboards apps
| Container Artifact Gen (159 apps) | ADM | Dockerfiles, K8s manifests, Helm charts | 25 |  |  | 25 |  |  | 25 |  |  | Container Generator: AI source-code analysis, Dockerfile/K8s manifest auto-generation, Helm chart creation | Container Artifact Gen | 159 apps x AI source analysis
| Framework Upgrades (.Net/Java) | ADM | .Net/Java upgrades for containerization | 20 |  |  | 20 |  |  | 20 |  |  | Upgrade Advisor: Dependency graph analysis, upgrade path recommendation, breaking change detection | Framework Upgrades | Semi-auto, 40% residual manual
| Middleware Upgrades & Jobs | ADM | Middleware versions, batch job migration | 15 |  |  | 15 |  |  | 15 |  |  | Config Extractor: Middleware config extraction, job definition migration, partial automation | Middleware Migration | Config extraction + manual verification
| DB Schema Conversion | CIS CLD | Convert stored procs, triggers, functions | 20 |  |  | 20 |  |  | 22 |  |  | DB Remediation Engine: SCT auto-conversion + AI-assisted fix for unconverted objects | Schema Conversion | SCT auto-converts 80%, AI fixes rest
| Migration Rehearsal (Dry Run) | CIS CLD + ADM | Full rehearsal per wave in non-prod | 15 |  |  | 15 |  |  | 18 |  |  | Rehearsal Orchestrator: Automated rehearsal execution, outcome validation, gap detection | Rehearsal / Dry Run | AI orchestrates + validates outcomes
| Integration Testing | IQE | Validate connectivity, APIs, data integrity | 15 |  |  | 15 |  |  | 18 |  |  | Test Generator: API connectivity test generation, data integrity validation scripts | NFR Testing (30%) | IQE functional validation post-rehearsal
| Security Validation | CyberSec | Vulnerability scans, compliance per wave | 8 |  |  | 8 |  |  | 10 |  |  | Guardrails Engine: Pre-flight compliance scan, code security analysis, violation detection | Compliance & Security | PG&E NERC CIP requirements
| Pre-Migration Patch Execution | CyberSec | Patch critical/high CVEs on source before cutover | 12 |  |  | 12 |  |  | 15 |  |  | Patch Executor: SSM/Ansible automated patching, post-patch validation, compliance verification | Vuln Patch Execution | Must-fix before migration per PG&E policy
Phase 4: Migration Execution
| Wave 1: Pilot (10-15 apps) | CIS CLD | Pilot batch across all platforms | 8 |  |  | 8 |  |  | 10 |  |  | Execution Engine: Orchestrated pilot migration, automated validation, progress tracking | Rehost Execution | Validate patterns before scale
| Rehost / Lift-and-Shift (179 apps) | CIS CLD + EIT | V->V, P->V, HyperVisor-Replace | 40 |  |  | 45 |  |  | 50 |  |  | MGN/ASR Orchestrator: Automated replication, cutover scheduling, post-migration health check | Rehost Execution | 179 apps x 0.5d = ~90 total, split by platform
| Replatform (OS/DB Upgrade) | CIS CLD | OS upgrades, DB upgrades during migration | 25 |  |  | 25 |  |  | 28 |  |  | Upgrade Executor: Scripted OS/DB upgrades, pre/post validation, automated smoke tests | Replatform Execution | CIS CLD-led, scripted upgrades
| Containerize Execution (159 apps) | ADM | Docker build, push, EKS/AKS deploy | 35 |  |  | 35 |  |  | 35 |  |  | CI/CD Pipeline: Docker build+push, K8s deployment, automated health checks, canary validation | Containerize Execution | 159 apps x 1.2d = ~191 total, split
| Framework Replace (5 apps) | ADM | .Net/Java framework replacement | 8 |  |  | 8 |  |  | 8 |  |  | Framework Migrator: Code transformation assistance, dependency resolution | Framework Upgrades | 5 apps, high complexity per app
| Retire (24 apps) | CIS CLD | Decommission retired applications | 5 |  |  | 5 |  |  | 5 |  |  | Dependency Validator: Pre-retirement dependency check, safe decommission confirmation | License Analysis | Dependency check + decommission
| Database Migration (DMS/CDC) | CIS CLD | CDC replication and cutover | 20 |  |  | 20 |  |  | 22 |  |  | DMS Orchestrator: CDC task creation, replication monitoring, cutover execution | Schema Conversion | DMS tasks across all DB targets
| DNS Cutover & Traffic Shift | CIS CLD | Switch DNS per wave, validate | 5 |  |  | 5 |  |  | 5 |  |  | DNS Cutover Engine: Automated DNS switch, traffic validation, rollback-ready | Rehost Execution | Orchestrated cutover
| Rollback Execution | CIS CLD | Rollback for failed migrations | 5 |  |  | 5 |  |  | 5 |  |  | Rollback Engine: Pre-built rollback scripts, one-click execution, state restoration | Rehost Execution | Pre-built rollback scripts
| Post-Migration Vuln Scan (per wave) | CyberSec | Scan migrated workloads for new vulns introduced during migration | 10 |  |  | 10 |  |  | 12 |  |  | Vuln Scanner: Post-migration scan, delta report vs baseline, new CVE detection | Vuln Discovery Scan | Compare against pre-migration baseline
| Vuln Remediation - Migrated Targets | CyberSec | Patch any new vulns found on target cloud instances | 8 |  |  | 8 |  |  | 10 |  |  | Patch Executor: Target-side patching via SSM/Ansible, automated post-patch health check | Vuln Patch Execution | New vulns from migration or cloud-specific CVEs
Phase 4a: Testing (IQE-Led)
| FR Testing - Rearchitect (60%) | IQE | Full FR for 159 containerized apps @ 60% | 45 |  |  | 45 |  |  | 45 |  |  | Test Suite Generator: AI-generated FR test cases, parallel automated execution, AI defect triage | FR Testing (60%) | 159 apps x 3d x 60% effort = per platform
| FR Testing - Framework Replace (40%) | IQE | Targeted FR for 5 framework-replaced apps | 8 |  |  | 8 |  |  | 8 |  |  | Test Suite Generator: Targeted FR test generation for framework-changed components | FR Testing (60%) | 5 apps x 5d x 40% effort
| NFR Testing - Replatform (30%) | IQE | Perf/load/stress for replatformed apps | 20 |  |  | 20 |  |  | 22 |  |  | Perf Test Generator: Auto-generated JMeter/Gatling scripts, AI performance analysis | NFR Testing (30%) | Full perf baseline validation
| NFR Testing - Replatform Lite (20%) | IQE | Basic perf for lift-and-shift apps | 12 |  |  | 12 |  |  | 14 |  |  | Smoke Test Suite: Lightweight perf validation, baseline comparison, pass/fail automation | NFR Testing (30%) | Smoke + basic perf validation
| Security Testing (Pen Test) | IQE + CyberSec | Pen testing for tier-1 post-migration | 10 |  |  | 10 |  |  | 10 |  |  | Security Scanner: Automated vuln scan, pen test assist, compliance report generation | NFR Testing (30%) | PG&E mandatory for critical apps
| UAT Coordination | IQE | Coordinate UAT with business teams | 10 |  |  | 10 |  |  | 10 |  |  | UAT Dashboard: Test progress tracking, defect management, sign-off workflow | NFR Testing (30%) | IQE facilitates, business executes
Phase 5: Post-Migration Optimize
| Right-Sizing (4273 servers) | CIS CLD | Optimize instance sizes from usage data | 12 |  |  | 12 |  |  | 12 |  |  | Right-Sizing Engine: ML-based 30-day usage analysis, optimal SKU recommendation | Right-Sizing | AI from 30-day usage analysis
| Cost Optimization (FinOps) | CIS CLD | Reservations, spot, savings plans | 8 |  |  | 8 |  |  | 8 |  |  | FinOps Engine: RI/SP recommendation, spot eligibility, daily spend tracking | TCO / Cost Modeling | AI identifies savings opportunities
| Monitoring & Alerting Setup | CIS CLD + EIT | CloudWatch/Azure Monitor/Grafana | 8 |  |  | 8 |  |  | 10 |  |  | Monitoring Templates: Pre-built dashboards, alert rules, Grafana integration | Monitoring Setup | Template + PG&E custom alerts
| Documentation & Handoff | All Teams | Runbooks, architecture docs, KT | 10 |  |  | 10 |  |  | 10 |  |  | Doc Generator: Auto-generated runbooks, architecture diagrams, migration audit trail | Compliance & Security | AI generates draft docs from migration data
| Decommission Source Infra | CIS CLD + EIT | Shut down on-prem after validation | 10 |  |  | 10 |  |  | 10 |  |  | Decommission Validator: Dependency re-check, safe shutdown confirmation, audit log | License Analysis | Staged per wave after 30-day soak
| Continuous Vuln Monitoring Setup | CyberSec | Configure ongoing vuln scanning, auto-ticketing for new CVEs | 8 |  |  | 8 |  |  | 10 |  |  | Continuous Vuln Monitor: Scheduled scan config, CVSS threshold alerts, JIRA/ServiceNow auto-ticketing | Vuln Continuous Monitoring | Ongoing post-migration vulnerability hygiene
| Vuln Compliance Dashboard | CyberSec | Build vuln posture dashboard for PG&E exec reporting | 5 |  |  | 5 |  |  | 5 |  |  | Vuln Dashboard: Grafana vuln posture dashboard, CVSS trend charts, SLA compliance tracking | Vuln Continuous Monitoring | PG&E exec visibility into security posture
TOTAL
AI Accelerator Savings Summary
| Platform | Apps | Servers | Traditional Days | AI Days | Days Saved | % Saved | Months Saved
| AWS | 107 | 719
| Azure | 145 | 852
| Azure Local/HyperV | 130 | 2702

## Cost Estimation
PG&E Migration Cost - 4-Team Model, 2-Year Projection
415 Apps ¦ 4,273 Servers ¦ Yellow = adjustable input ¦ All costs formula-driven
Section A: Team Role Rate Card
Team | Role | Hourly ($) | Daily ($) (8 hrs) | Monthly ($) (22 days) | FTE Count | Monthly Cost ($) | Annual Cost ($) | Location
CIS CLD | Cloud Migration Lead | 180 |  |  | 1 |  |  | Onshore
CIS CLD | Sr. Migration Engineer | 150 |  |  | 4 |  |  | Offshore
CIS CLD | Migration Engineer | 100 |  |  | 6 |  |  | Offshore
CIS CLD | DB Migration Specialist | 160 |  |  | 2 |  |  | Offshore
CIS CLD | DevOps / SRE Engineer | 140 |  |  | 2 |  |  | Offshore
CIS CLD | Network Engineer (App-Level) | 125 |  |  | 0 |  |  | Offshore
CIS CLD | Project Manager | 155 |  |  | 1 |  |  | Onshore
CIS EIT | Azure Local / HyperV Lead | 170 |  |  | 1 |  |  | Onshore
CIS EIT | Infrastructure Engineer | 130 |  |  | 3 |  |  | Offshore
CIS EIT | Network Engineer (App-Level) | 125 |  |  | 0 |  |  | Offshore
ADM | App Modernization Lead | 175 |  |  | 1 |  |  | Onshore
ADM | Sr. App Developer | 145 |  |  | 4 |  |  | Offshore
ADM | App Developer | 100 |  |  | 6 |  |  | Offshore
ADM | Middleware Engineer | 135 |  |  | 2 |  |  | Offshore
ADM | DevOps (K8s) | 140 |  |  | 2 |  |  | Offshore
IQE | Test Lead | 150 |  |  | 1 |  |  | Onshore
IQE | Sr. Test Engineer (FR) | 120 |  |  | 3 |  |  | Offshore
IQE | Perf Test Engineer (NFR) | 130 |  |  | 2 |  |  | Offshore
IQE | Security Test Engineer | 140 |  |  | 1 |  |  | Offshore
IQE | Test Automation Engineer | 125 |  |  | 2 |  |  | Offshore
CyberSec | Security Analyst | 155 |  |  | 1 |  |  | Onshore
CyberSec | Vuln Mgmt Engineer | 140 |  |  | 2 |  |  | Offshore
FinOps | FinOps Analyst | 130 |  |  | 1 |  |  | Offshore
TOTAL ALL TEAMS
Section B: Phase-Based Cost (Duration from Migration Activities tab)
Phase | Primary Team | Trad Days | AI Days | Team FTEs | Blended Daily Rate ($) | Traditional Cost ($) | AI Cost ($) | Savings ($) | Savings % | Cloud Infra $/Month | Phase Total AI ($)
Discovery & Assessment [COMPLETED] | CIS CLD + EIT | 0 | 0 | 0 | 1050 |  |  |  |  | 0
Planning & Design | CIS CLD + ADM | 68 | 14 | 14 | 1100 |  |  |  |  | 500
Build & Prepare | All Teams | 108 | 30 | 18 | 1050 |  |  |  |  | 1000
Migration Execution - Rehost | CIS CLD + EIT | 83 | 27 | 14 | 1050 |  |  |  |  | 0
Migration Execution - Containerize | ADM | 43 | 15 | 15 | 1000 |  |  |  |  | 0
Migration Execution - Other | CIS CLD | 30 | 11 | 8 | 1100 |  |  |  |  | 0
Testing - FR (Rearchitect 60%) | IQE | 53 | 24 | 9 | 1000 |  |  |  |  | 0
Testing - NFR (Replatform 30%) | IQE | 32 | 13 | 6 | 1050 |  |  |  |  | 0
Testing - Security & UAT | IQE + CyberSec | 20 | 9 | 5 | 1100 |  |  |  |  | 0
Vulnerability Management (All Phases) | CyberSec | 68 | 22 | 4 | 1100 |  |  |  |  | 0
Post-Migration Optimize | CIS CLD | 48 | 16 | 8 | 1050 |  |  |  |  | 0
TOTAL ALL PHASES
Section C: 2-Year Cost Projection
Cost Category | Year 1 ($) | Year 2 ($) | 2-Year Total ($) | Notes
Migration Labor (AI Accelerated) |  |  |  | Year 2 = 15% steady-state
Cloud Infrastructure (App-Level Only) |  |  |  | PG&E bears LZ/network; app-level only
AI Platform License | 48000 | 48000 |  | CloudMigrate.store enterprise
Tooling & 3rd Party | 25000 | 18000 |  | DMS, Terraform Cloud, etc.
Training & Enablement | 20000 | 8000 |  | All 4 teams
CyberSec & Compliance | 35000 | 25000 |  | NERC CIP ongoing
Vuln Mgmt Tooling (Nessus/Qualys) | 18000 | 18000 |  | Annual vuln scanner license
Contingency (12%) |  |  |  | 4273-server migration buffer
GRAND TOTAL (2 YEARS)
Traditional Cost (2 Years - No AI) |  |  |  | Trad labor + 25% Year 2
NET SAVINGS WITH AI |  |  | % Savings

## Executive Summary
PG&E Migration - Executive Summary
Metric | Value
Total Applications | 415
Total Servers | 4273
Traditional Duration - AWS (Days)
AI-Accelerated Duration - AWS (Days)
Time Saved % - AWS
Traditional Migration Cost ($)
AI-Accelerated Cost ($)
2-Year Grand Total ($)
Net Savings vs Traditional ($)
Total FTEs
Key: AI Days = Traditional Days x AI Factor (from AI Assumptions tab)
Change any yellow cell to model different scenarios. All formulas auto-update.

## Executive Dashboard
PG&E Cloud Migration — Executive Dashboard
415 Applications ¦ 4,273 Servers ¦ 5 Teams ¦ AI-Accelerated with CloudMigrate.store
Duration Comparison (Days) |  |  |  | KEY METRICS
Platform | Traditional | AI-Accelerated | Days Saved | Applications | 415
AWS (107 apps) |  |  |  | Servers | 4,273
Azure (145 apps) |  |  |  | Target Platforms | AWS + Azure + AzLocal
Azure Local/HV (130 apps) |  |  |  | Teams | CIS CLD + EIT + ADM + IQE
Time Saved (AWS)
Cost Comparison ($) |  |  |  | Cost Savings ($)
Category | Amount ($) |  |  | 2-Year Investment
Traditional Migration (2yr) |  |  |  | Total FTEs
AI-Accelerated (2yr Grand Total)
Net Savings |  |  |  | PG&E Provides | LZ + Network + Infra
|  |  |  | Infosys Delivers | Migration + Modernization
|  |  |  | AI Accelerator | CloudMigrate.store
Phase Effort Breakdown (AI Days)
Phase | AI Days
Discovery
Planning
Build
Rehost Exec
Containerize Exec
Other Exec
FR Testing
NFR Testing
Security/UAT
Vuln Mgmt
Optimize
Team FTE Allocation
Team | FTEs
CIS CLD (Rehost/Replatform) | 17
CIS EIT (Azure Local/HyperV) | 5
ADM (Containerize/Framework) | 15
IQE (Testing) | 9
CyberSec (Security/VulnMgmt) | 4
FinOps | 1
App Distribution by Journey |  | Servers by Platform
Journey | Apps | Platform | Servers
Lift-and-Shift | 179 | AWS | 719
Containerize | 159 | Azure | 852
TBD | 31 | Azure Local | 1295
Retire | 24 | HyperV | 356
Framework Replace | 17 | Physical | 164
Fresh Install/Transform | 5 | SaaS/PaaS | 126
|  | TBD | 761

## Team Revenue View
PG&E Migration — Team-wise FTE, Cost & Revenue Breakdown
All values formula-driven from Cost Estimation tab ¦ Yellow = adjustable inputs ¦ Margin % adjustable per team
Section A: Team FTE & Monthly/Annual Cost (from Cost Estimation Rate Card)
Team | Roles | Total FTEs | Avg Hourly Rate ($) | Monthly Cost ($) | Annual Cost ($) | Scope / Responsibility
CIS CLD | Cloud Migration Lead, Sr. Migration Engineers (4), Migration Engineers (6), DB Specialist (2), DevOps (2), PM |  |  |  |  | Rehost, Replatform, DB Migration, Wave Planning on AWS & Azure
CIS EIT | Azure Local/HyperV Lead, Infrastructure Engineers (3) |  |  |  |  | Azure Local & HyperV workload onboarding, cluster validation
ADM | App Modernization Lead, Sr. Developers (4), Developers (6), Middleware (2), DevOps K8s (2) |  |  |  |  | Containerization (159 apps), .Net/Java upgrades, Middleware migration
IQE | Test Lead, SR Test Engineers FR (3), Perf NFR (2), Security (1), Automation (2) |  |  |  |  | FR Testing 60%, NFR Testing 30%, Security Testing, UAT coordination
CyberSec (Vuln Mgmt) | Security Analyst, Vuln Mgmt Engineers (2) |  |  |  |  | Vulnerability scanning, remediation, patching, compliance, NERC CIP
FinOps | FinOps Analyst |  |  |  |  | Cost optimization, RI/SP recommendations
TOTAL
Section B: Team-wise 2-Year Revenue Model (Margin-Adjustable)
Team | FTEs | Year 1 Duration (Mo) | Year 1 Cost ($) | Year 2 Duration (Mo) | Year 2 Cost ($) | 2-Year Total Cost ($) | Margin % (Adjust) | Year 1 Revenue ($) | Year 2 Revenue ($) | 2-Year Revenue ($) | % of Total Revenue
CIS CLD |  | 12 |  | 3 |  |  | 25%
CIS EIT |  | 10 |  | 2 |  |  | 25%
ADM |  | 12 |  | 3 |  |  | 25%
IQE |  | 10 |  | 2 |  |  | 22%
CyberSec (Vuln Mgmt) |  | 12 |  | 6 |  |  | 28%
FinOps |  | 8 |  | 4 |  |  | 20%
TOTAL | [10 empty] | 100%
Section C: Key Revenue Metrics
Total 2-Year Cost (All Teams)
Total 2-Year Revenue (All Teams)
Total Gross Margin ($)
Blended Margin %
Largest Team by Revenue | CIS CLD
Largest Team by FTEs
CyberSec/Vuln Mgmt Revenue Share
Total FTEs Deployed
Avg Revenue per FTE (2yr)

## Tool vs Industry Benchmark
CloudMigrate.store vs Industry Standard — Honest Benchmark Comparison
Industry = Generic tooling (AWS Migration Hub + separate SCT + separate Terraform + manual glue) ¦ CloudMigrate = Integrated AI platform
Category | Industry Std Savings % | CloudMigrate Savings % | Delta (Improvement) | Industry Standard Approach (Generic Tools) | CloudMigrate.store Advantage (What Our Tool Adds) | Why The Delta (Honest Assessment) | Risk if Overclaimed | Confidence Level | Industry Reference
Infrastructure Discovery | 65% | 72% |  | AWS Migration Hub + Azure Migrate run separately; results in 2 spreadsheets that need manual merging for multi-cloud view | Single-pane discovery across AWS+Azure+AzLocal with unified topology map, 29 component types auto-detected, cross-cloud dependency view | +7%: Unified multi-cloud view eliminates manual merge of separate tool outputs. For 4273 servers across 3 clouds, this saves 2-3 days of reconciliation per discovery cycle | Over-claim if PG&E has heavily air-gapped systems that no tool can reach | High | Gartner 2024 + internal benchmark
App Dependency Mapping | 60% | 65% |  | ServiceNow CMDB + Dynatrace/AppDynamics for runtime deps; still misses 30-40% of dependencies requiring manual app-owner interviews | Network flow tracing + CMDB correlation + AI-powered graph building in one workflow; reduces manual interview rounds from 3 to 1 | +5%: AI graph building catches cross-app patterns that individual tools miss. Conservative delta — dependency mapping is inherently hard regardless of tooling | Dependency mapping accuracy is never 100%; app owner validation always needed | Medium | Gartner 2024
Database Analysis | 65% | 70% |  | AWS SCT + Azure DMA run separately; conversion reports need manual cross-referencing; no AI-assisted fix suggestions | DB Remediation Engine runs SCT + provides AI-assisted fix suggestions for unconverted objects; cross-cloud DB compatibility matrix in one view | +5%: AI-assisted fix suggestions for unconverted stored procs reduce manual effort. SCT still does the heavy lifting — our tool adds the remediation layer | Complex PL/SQL (PG&E Oracle legacy) may still need DBA manual rewrite regardless | Medium-High | AWS SCT docs
TCO / Cost Modeling | 70% | 75% |  | AWS Pricing Calculator + Azure TCO Calculator run separately; manual Excel consolidation for multi-cloud comparison | MCP cloud-cost service generates unified multi-cloud TCO from discovery data with live pricing APIs; auto-comparison across AWS/Azure/AzLocal | +5%: Eliminates manual multi-cloud spreadsheet merging. Auto-links TCO to actual discovered inventory rather than manual input estimates | EDP/RI negotiation and business assumptions still need stakeholder input regardless | High | AWS Pricing + Cobalt
Performance Baseline | 70% | 70% |  | CloudWatch + Azure Monitor + custom scripts; metric collection well-automated by cloud-native tools | Aggregates metrics across all 3 clouds in unified baseline dashboard; but cloud-native tools already do this well individually | 0%: No significant delta. Cloud-native monitoring tools are mature. Our value is unified view, not faster collection | Honest: cloud-native tools are already excellent here | High | AWS CloudWatch
Compliance & Security (NERC CIP) | 50% | 52% |  | Separate compliance scanning tools (Prisma, Prowler) + manual NERC CIP evidence collection; heavily regulated = heavily manual | MCP compliance-framework service + guardrails engine scan against frameworks; but NERC CIP evidence collection and regulatory sign-off remain manual regardless | +2%: Marginal improvement. Compliance for regulated utilities is fundamentally manual-intensive. Our scanning is faster but the bottleneck is human review and regulatory evidence | DO NOT overclaim here. NERC CIP compliance is 70%+ manual — no tool changes this | Low | NERC CIP reqs
Wave Planning | 60% | 65% |  | Manual wave grouping using dependency data from discovery; spreadsheet-based optimization; stakeholder negotiation is the bottleneck | Graph-based wave optimizer uses dependency data + risk scoring + parallel simulation; generates optimal wave plan that would take weeks manually | +5%: Algorithm-optimized wave grouping is genuinely faster than manual spreadsheet analysis. But stakeholder alignment (50% of wave planning effort) is unchanged | Stakeholder negotiation window constraints cannot be automated | Medium-High | McKinsey 2023
Terraform/IaC Generation | 70% | 75% |  | Manual HCL writing using Terraform docs + module registry; separate tool from discovery — no auto-population from discovered inventory | MCP terraform-generator auto-generates HCL from discovery data; app-level resources (SGs, LBs, DNS) pre-populated with actual values from inventory | +5%: Auto-population from discovery data eliminates the manual step of translating inventory into Terraform variables. Module customization and PR review still manual | Complex modules (custom VPC peering, Transit Gateway) still need manual HCL | High | HashiCorp 2024
Container Artifact Gen | 60% | 65% |  | Manual Dockerfile writing + K8s manifest creation; tools like Kompose help but dont analyze source code | AI source-code analysis generates Dockerfiles + K8s manifests + Helm charts tailored to actual app stack; identifies runtime dependencies automatically | +5%: Source code analysis catches dependencies that manual Dockerfile writing misses. But custom configs, multi-stage builds, sidecar patterns still need manual tuning | Non-standard stacks (legacy .NET Framework 4.x, COBOL wrappers) need manual Dockerfiles | Medium | CNCF 2024
Framework Upgrades | 45% | 47% |  | Manual code refactoring with IDE assistance; GitHub Copilot helps but doesnt understand migration context | Upgrade Advisor identifies breaking changes + dependency conflicts in migration context; but actual code changes are still manual developer work | +2%: Marginal. Code refactoring is fundamentally a developer task. Our tool helps with identification, not execution. Honest: AI assist is ~30-50% for code changes (GitHub Copilot data) | DO NOT overclaim. Framework upgrades = developer skill, not tool capability | Low | GitHub Copilot
Middleware Migration | 45% | 47% |  | Manual config extraction + version migration; custom plugins need per-plugin analysis | Config extraction automation + partial middleware mapping; but version differences and custom plugins still need manual migration | +2%: Marginal. Similar to framework upgrades — tool helps with config extraction but the hard part (plugin compat, job scheduling) is manual | Middleware migration complexity varies wildly by product (WebLogic vs Tomcat vs IIS) | Low | Industry avg
Schema Conversion | 60% | 65% |  | AWS SCT auto-converts 60-80% of simple objects; complex PL/SQL needs manual DBA rewrite; no AI-assisted suggestions | DB Remediation Engine wraps SCT + adds AI-suggested fixes for unconverted objects; pattern matching for common PL/SQL-to-PostgreSQL transforms | +5%: AI pattern matching handles common conversion patterns that SCT marks as "manual action needed". Saves DBA time on repetitive patterns, but complex custom PL/SQL still needs expert | PG&E Oracle databases with 10+ years of PL/SQL — complexity may exceed AI pattern library | Medium | AWS SCT tiers
Rehearsal / Dry Run | 55% | 60% |  | Manual rehearsal with runbook; separate monitoring to validate outcomes; post-rehearsal findings tracked in spreadsheet | Orchestrated rehearsal execution with automated outcome validation, gap detection, and finding prioritization in one workflow | +5%: Orchestrated execution + automated validation saves 1-2 days per rehearsal wave vs manual runbook execution. Findings auto-prioritized instead of manual triage | Complex failures still need human root-cause analysis | Medium-High | AWS Playbook
Rehost Execution | 60% | 63% |  | AWS MGN / Azure ASR automate replication (biggest time saver); cutover coordination, DNS switch, validation are manual across separate tools | Unified execution engine orchestrates MGN/ASR replication + cutover scheduling + DNS switch + health check in one pipeline; rollback pre-built | +3%: Orchestrated pipeline reduces handoff time between replication-complete and cutover-execute. MGN/ASR do the heavy lifting regardless — our value is coordination layer | Cutover windows are business-driven, not tool-driven | Medium | AWS MGN + Gartner
Replatform Execution | 55% | 57% |  | Scripted OS/DB upgrades via SSM/Ansible; pre/post validation manual; separate tooling for each step | Upgrade executor chains SSM scripts + validation in orchestrated workflow; auto-generated pre/post validation checks from discovery baselines | +2%: Auto-generated validation checks from baselines save manual checklist creation. Upgrade scripts themselves are standard SSM/Ansible regardless of tool | DB upgrades (especially Oracle -> Aurora) have unpredictable compatibility issues | Medium | Industry avg
Containerize Execution | 55% | 58% |  | CI/CD pipeline (Jenkins/GitHub Actions) for build-push-deploy; manual smoke testing and config validation | Integrated CI/CD pipeline with automated health checks + canary validation; pre-configured from artifact generation phase | +3%: Pre-configured pipeline from artifact gen phase eliminates manual CI/CD setup. Health checks auto-generated from discovery baselines. Smoke testing still manual | App-specific validation (business logic) cannot be automated | Medium | CNCF 2024
FR Testing (60% effort) | 50% | 53% |  | Manual test case design + Selenium/Cypress execution; test automation frameworks exist but setup is per-project | AI-generated test cases from app behavior analysis + parallel execution framework; reduces test design time but defect triage still manual | +3%: AI test case generation saves 20-30% of test design effort (the other 50% is execution which is already automatable). Defect triage and root cause = human | Business-logic test cases require domain knowledge no AI can replace | Medium | Forrester TEI
NFR Testing (30% effort) | 50% | 52% |  | Manual JMeter/Gatling scripting + result analysis; performance baselines compared manually | Auto-generated load scripts from traffic patterns + AI performance comparison against discovery baselines | +2%: Auto-generated scripts from real traffic patterns more representative than manually designed scenarios. But bottleneck identification and tuning are human tasks | Performance issues often root-cause to architecture, not configuration | Medium | Gartner
Right-Sizing | 70% | 72% |  | AWS Compute Optimizer / Azure Advisor — already highly accurate (80%+ match rate); cloud-native tools are mature here | Unified right-sizing across AWS+Azure+AzLocal in single view; but cloud-native tools already do this well individually | +2%: Marginal — unified view is convenient but cloud-native tools are excellent. Our value is cross-cloud comparison, not better analysis | Honest: AWS Compute Optimizer is hard to beat on AWS-specific sizing | Medium-High | AWS Compute Opt
Monitoring Setup | 55% | 57% |  | Terraform modules for CloudWatch/Azure Monitor + manual Grafana dashboard creation | Pre-built monitoring templates + Grafana integration auto-deployed from discovery metadata; PG&E-specific SLOs still manual | +2%: Pre-built templates from discovery metadata save dashboard creation time. Alert thresholds auto-suggested from baselines. Custom SLOs remain manual | PG&E-specific operational requirements drive custom alerting regardless | Medium | Datadog/Grafana
Vuln Discovery Scan | 65% | 68% |  | Nessus/Qualys scan separately + manual CVSS triage in spreadsheet; separate from migration workflow | Integrated vuln scanning in migration pipeline + CVSS auto-triage + false-positive filtering using migration context (e.g., server being retired = deprioritize) | +3%: Migration-context-aware triage is the differentiator. Generic vuln scanners dont know which servers are being retired vs migrated — our tool does, reducing unnecessary triage | Critical CVEs on NERC CIP systems still need manual human review regardless | Medium-High | Tenable/Qualys
Vuln Remediation Planning | 55% | 58% |  | Manual CVE-to-patch mapping + change request creation in ServiceNow; patch scheduling around change windows | AI-prioritized remediation plan with auto-generated runbooks + change request drafts; migration-aware scheduling (patch before migrate, not after) | +3%: Migration-aware scheduling prevents patch-then-migrate vs migrate-then-patch conflicts. Auto-generated runbooks save 1-2 days per wave planning cycle | CAB approval and change window negotiation are organizational, not tool-solvable | Medium | ServiceNow VR
Vuln Patch Execution | 55% | 57% |  | SSM/Ansible patch automation + manual validation; compliance evidence collected separately | Orchestrated patching with auto-generated compliance evidence trail; NERC CIP audit-ready output | +2%: Auto-generated compliance evidence trail saves manual documentation. But NERC CIP sign-off is still manual regulatory process | Patch rollback scenarios still need human decision-making | Medium | AWS SSM
Vuln Continuous Monitoring | 60% | 62% |  | Scheduled scans + manual ticket creation in JIRA/ServiceNow; periodic reporting | Continuous scanning + auto-ticketing + Grafana vuln posture dashboard with SLA tracking | +2%: Auto-ticketing and dashboard are convenient but not transformational. The real work is remediation follow-up which is manual regardless | Dashboard ≠ remediation. Pretty charts dont fix CVEs | Medium | Industry avg
WEIGHTED AVERAGE | [5 empty] | CloudMigrate.store provides ~3-4% incremental improvement over industry standard on average
Honest Summary: Where CloudMigrate.store Genuinely Adds Value
STRONG ADVANTAGES (+5-7% over industry): Integration & Multi-Cloud Unification
1. UNIFIED MULTI-CLOUD DISCOVERY: Single scan across AWS+Azure+AzLocal vs running 3 separate tools and merging spreadsheets. For 4273 servers across 3 clouds, this saves 3-5 days of reconciliation.
2. DISCOVERY-TO-IaC PIPELINE: Terraform auto-generated FROM discovery data — no manual translation of inventory into HCL variables. Industry tools have a gap between discovery output and IaC input.
3. DISCOVERY-TO-TCO PIPELINE: TCO auto-generated from actual inventory vs manual AWS/Azure pricing calculator input. Eliminates data-entry errors and multi-cloud comparison spreadsheets.
4. DB REMEDIATION LAYER: Goes beyond SCT reporting — provides AI-suggested fixes for unconverted objects. SCT tells you what failed; our tool suggests how to fix it.
5. MIGRATION-CONTEXT VULN TRIAGE: Generic vuln scanners dont know migration context. Our tool deprioritizes CVEs on servers being retired, prioritizes servers being migrated first.
MODERATE ADVANTAGES (+2-3%): Orchestration & Workflow Automation
6. ORCHESTRATED EXECUTION: Single pipeline for replication -> cutover -> DNS -> validation vs manual handoffs between MGN console, Route53, and monitoring dashboard.
7. REHEARSAL ORCHESTRATION: Automated rehearsal execution + outcome validation vs manual runbook + spreadsheet checklist.
8. AI TEST GENERATION: Test cases auto-generated from app behavior analysis. Saves ~20-30% of test design time. Execution speed is same (Selenium/Cypress).
9. PRE-BUILT MONITORING: Templates auto-deployed from discovery metadata. Saves dashboard creation time but custom PG&E SLOs still manual.
HONEST LIMITATIONS (0-2%): Areas Where Our Tool Doesnt Significantly Outperform
10. COMPLIANCE / NERC CIP: Regulatory compliance is fundamentally manual. Our scanning is marginally faster but the bottleneck (evidence collection, auditor review) is unchanged. +2% max.
11. FRAMEWORK UPGRADES: Code refactoring is a developer skill. Our Upgrade Advisor helps with identification, but actual .NET/Java code changes need developers. +2% max.
12. MIDDLEWARE MIGRATION: Custom plugin compatibility is per-product analysis. Tool can extract configs but cant validate WebLogic-to-Tomcat plugin compatibility automatically.
13. PERFORMANCE BASELINE: Cloud-native monitoring (CloudWatch, Azure Monitor) is already excellent. Our unified view is convenient but doesnt collect metrics faster. 0% delta.
14. RIGHT-SIZING: AWS Compute Optimizer is genuinely best-in-class for AWS. Our value is cross-cloud comparison, not better per-cloud sizing. +2% max.
BOTTOM LINE FOR EXECUTIVES
CloudMigrate.store does NOT claim to be 2x faster than industry tools. It provides a consistent 3-7% improvement in high-impact areas
through INTEGRATION (eliminating manual handoffs between 10+ separate tools) rather than making individual activities dramatically faster.
The real value proposition is: ONE PLATFORM replacing AWS Migration Hub + Azure Migrate + SCT + DMA + Terraform CLI + Nessus + JMeter + 5 spreadsheets.
Time saved = less from faster individual tasks, MORE from eliminated handoff/reconciliation overhead between disconnected tools.
Industry Standard Blended Savings: =B29 ¦ CloudMigrate Blended Savings: =C29 ¦ Net Improvement: =D29

## CM vs Matilda Summary
CloudMigrate.store vs Matilda Cloud — Head-to-Head Comparison
PG&E: 415 Apps ¦ 4,273 Servers ¦ Discovery & Assessment COMPLETED ¦ Remaining: Planning through Optimize
Section A: Timeline Comparison (Remaining Phases — Discovery DONE)
Metric | Traditional | CloudMigrate.store | Matilda Cloud | CM vs Matilda
Discovery & Assessment | COMPLETED | COMPLETED | COMPLETED | Both done
Remaining Duration (Days) | 553 | 181 | 200 |  |  | Traditional | CloudMigrate | Matilda
Remaining Duration (Months) | [5 empty] | 553 | 181 | 200
Time Saved vs Traditional (Days)
Time Saved vs Traditional (%) | [5 empty] | Traditional | CloudMigrate | Matilda
Estimated Completion | ~25 months | ~8 months | ~9 months | CM 1 month faster
Section B: 2-Year Cost Comparison (Discovery costs already incurred)
Cost Category | Traditional ($) | CloudMigrate ($) | Matilda ($) | CM Saves vs Matilda ($)
Phase Labor - Year 1 | 6708500 | 2079900 | 2299300
Cloud Infra (App-level, Y1) | 6000 | 6000 | 6000
AI Platform License (Y1) | 0 | 48000 | 45000
Tooling & 3rd Party (Y1) | 25000 | 25000 | 25000
Training (Y1) | 20000 | 20000 | 20000
CyberSec & Compliance (Y1) | 35000 | 35000 | 35000
Vuln Mgmt Tooling (Y1) | 18000 | 18000 | 18000
Contingency 12% (Y1)
YEAR 1 SUBTOTAL
Steady-State Labor (Y2)
Cloud Infra (Y2) | 5100 | 5100 | 5100
AI Platform License (Y2) | 0 | 48000 | 45000
Tooling (Y2) | 18000 | 18000 | 18000
Training (Y2) | 8000 | 8000 | 8000
CyberSec (Y2) | 25000 | 25000 | 25000
Vuln Tooling (Y2) | 18000 | 18000 | 18000
Contingency 12% (Y2)
YEAR 2 SUBTOTAL
2-YEAR GRAND TOTAL
Savings vs Traditional ($)
Savings vs Traditional (%)
CM Additional Savings over Matilda |  |  | CloudMigrate saves this much MORE than Matilda
Section C: Category-by-Category — Where Each Tool Wins
Category | CM Savings % | Matilda % | Delta | Winner | Why CloudMigrate Wins
Container Artifact Gen | 65% | 55% |  | CloudMigrate | AI source-code analysis vs basic Dockerfile templates
FR Testing (60%) | 53% | 45% |  | CloudMigrate | AI test case generation vs no test capability in Matilda
NFR Testing (30%) | 52% | 47% |  | CloudMigrate | Auto-generated load scripts from traffic patterns
Vuln Continuous Monitor | 62% | 55% |  | CloudMigrate | Integrated vuln scanning vs separate Nessus/Qualys
Containerize Execution | 58% | 52% |  | CloudMigrate | Native CI/CD pipeline vs external Jenkins orchestration
Vuln Discovery Scan | 68% | 62% |  | CloudMigrate | Migration-context CVSS triage (deprioritize retiring servers)
Vuln Remediation Plan | 58% | 52% |  | CloudMigrate | Migration-aware patch scheduling prevents conflicts
DB Analysis | 70% | 65% |  | CloudMigrate | AI-suggested fixes for unconverted objects beyond SCT
Schema Conversion | 65% | 60% |  | CloudMigrate | AI pattern matching for PL/SQL-to-PostgreSQL transforms
TCO / Cost Modeling | 75% | 70% |  | CloudMigrate | Unified multi-cloud TCO auto-linked to discovery inventory
Terraform/IaC Gen | 75% | 70% |  | CloudMigrate | Auto-populated HCL from discovery data vs manual variables
Infrastructure Discovery | 72% | 68% |  | CM (slight) | Unified multi-cloud single-pane vs separate scans per platform
Framework Upgrades | 47% | 42% |  | CloudMigrate | Upgrade Advisor with migration context; marginal difference
Wave Planning | 65% | 62% |  | CM (slight) | Graph optimizer with parallel simulation vs rule-based
Rehost Execution | 63% | 62% |  | Tied | Near parity — Matilda strong here (core strength)
Performance Baseline | 70% | 70% |  | Tied | Tied — both use cloud-native monitoring APIs
Right-Sizing | 72% | 70% |  | CM (slight) | Near parity — both wrap Compute Optimizer/Azure Advisor
Compliance (NERC CIP) | 52% | 50% |  | CM (slight) | Near parity — regulatory work is manual regardless
SCORECARD
CloudMigrate Wins: | 16
Matilda Wins: | 0
Tied: | 2
EXECUTIVE BOTTOM LINE
Discovery & Assessment: COMPLETED — no remaining cost or time for either tool.
CloudMigrate.store delivers the remaining migration in ~8 months for ~$2.9M (2-year total).
Matilda Cloud delivers the same scope in ~9 months for ~$3.2M (2-year total).
CloudMigrate advantage: 19 days faster + $271K cheaper than Matilda.
CloudMigrate wins in 14 of 18 categories — strongest in AI-augmented activities:
- Container artifact generation (+10%), Testing (+5-8%), Vuln management (+6-7%)
- DB analysis/schema conversion (+5%), Terraform/TCO auto-generation (+5%)
Matilda matches CloudMigrate in: Rehost execution, Performance baseline, Right-sizing.
These are areas where cloud-native tools (MGN, Compute Optimizer) do the heavy lifting regardless.
The real CloudMigrate differentiator: INTEGRATED AI PLATFORM replacing 10+ separate tools.
Matilda is a solid migration automation tool but lacks AI-augmented analysis, test generation,
vulnerability management, and end-to-end pipeline integration that CloudMigrate provides.

## Agentic AI Comparison
Agentic AI Capabilities — CloudMigrate.store vs Matilda vs Concierto
CloudMigrate.store: 10 AI Agents + 4 ML Models + 8 MCP Services + Guardrails ¦ Live on cloudmigrate.store
Section A: Agentic AI Capability Inventory
AI Capability | CloudMigrate.store | Matilda Cloud | Concierto Migrate | CM Advantage
AUTONOMOUS AI AGENTS
IAM Agent (design/create/cleanup roles) | YES - Claude-powered | NO | NO | Unique to CM
Cost/Sizing Agent (recommend + analyze) | YES - Claude-powered | NO | Partial (Maximize module) | CM: autonomous agent vs rule engine
Compliance Agent (framework checks) | YES - Claude-powered | NO | NO | Unique to CM
Observability Agent (design monitoring) | YES - Claude-powered | NO | Partial (Manage module) | CM: AI-designed vs templates
Containerization Agent (Dockerfile+K8s) | YES - Claude-powered | NO | YES (Modernize 5000+ rules) | Both strong, different approach
Wave Planning Agent (dependency analysis) | YES - Claude-powered | Rule-based | AI-based (CloudIgnite) | CM: AI agent vs rules/AI
DR Agent (design + failover runbook) | YES - Claude-powered | NO | NO | Unique to CM
Performance Baseline Agent | YES - Claude-powered | NO | NO | Unique to CM
Data Masking Agent (PII scan) | YES - Claude-powered | NO | NO | Unique to CM - GDPR/PCI compliance
Rollback Decision Agent (go/no-go) | YES - Claude-powered | NO | Rollback capability | CM: AI-driven decision vs manual
ML PREDICTION MODELS
App Classifier (91% accuracy) | YES - sklearn, 14 features | NO | NO | Unique to CM
Right-Sizer (ML-based) | YES - trained model | NO | YES (Maximize) | Both have, CM is ML-trained
Duration Predictor | YES - trained model | NO | NO | Unique to CM
Anomaly Detector | YES - trained model | NO | NO | Unique to CM
MCP MICROSERVICES (Dedicated)
Database Catalog Service | YES - port 8010 | NO | NO | Unique to CM
Compliance Framework Service | YES - port 8011 | NO | NO | Unique to CM
Cloud Cost Service | YES - port 8012 | NO | Partial (Maximize) | CM: dedicated microservice
Migration Tools Service | YES - port 8013 | NO | YES (CloudMach) | Both have execution engines
Enterprise Services | YES - port 8014 | NO | NO | Unique to CM
Analytics Service | YES - port 8015 | NO | Partial (Intelligence) | Both have analytics
Terraform Generator Service | YES - port 8016 | NO | NO | Unique to CM - auto IaC
Source Scanner Service | YES - port 8017 | NO | YES (Modernize) | Both scan source code
GUARDRAILS & SAFETY
Source Protection | YES - enforced | NO | NO | Unique to CM
Encryption Enforcement | YES - enforced | NO | NO | Unique to CM
Budget Guardrails | YES - max $500 per action | NO | NO | Unique to CM - prevents runaway costs
Code Scanning | YES - enabled | NO | YES (5000+ rules) | Both scan code, CM adds guardrails
Data Validation Required | YES - enforced | NO | NO | Unique to CM
AI FOUNDATION
LLM Integration | Claude AI (Anthropic) | None | Not disclosed | CM: Claude AI for reasoning
AI Chat/Assistant | YES - migration chat | NO | Zero-code interface | CM: AI chat, Concierto: UI
Streaming AI Responses | YES - SSE streaming | NO | NO | Unique to CM
Agentic Memory (per project) | YES - context retention | NO | NO | Unique to CM - learns per project
API Routes (Agentic) | 39 dedicated routes | 0 | ~10 (est.) | CM: 39 vs 0-10
Section B: Agentic AI Scorecard
Metric | CloudMigrate | Matilda | Concierto
Autonomous AI Agents | 10 | 0 | 2
ML Prediction Models | 4 | 0 | 1
MCP Microservices | 8 | 0 | 3
Guardrails & Safety Controls | 5 | 0 | 1
LLM Integration (Claude AI) | YES | NO | NO
Agentic API Routes | 39 | 0 | ~10
AI Chat/Streaming | YES | NO | UI-based
Project Memory/Context | YES | NO | NO
TOTAL AI CAPABILITIES | 10 agents + 4 ML + 8 MCP + guardrails | 0 agents, rule-based only | 2 partial, AI in discovery+modernize
Section C: How Agentic AI Translates to Migration Savings
AI Capability | Migration Phase Impacted | Savings Impact | Why It Matters for PG&E
IAM Agent | Build & Execution | +3-5% on LZ/provisioning | Auto-designs IAM roles per app — 415 apps x manual role design = weeks saved
Compliance Agent | All phases | +2% on compliance | Auto-checks NERC CIP frameworks — reduces manual audit prep by 50%
Containerization Agent | Build (159 apps) | +5-10% on container gen | AI-generates Dockerfiles from source — 159 apps containerized faster
Wave Planning Agent | Planning | +3-5% on wave planning | AI-optimized dependency grouping — 415 apps across 7 waves
DR Agent | Planning + Post-migration | +2% on DR strategy | Auto-generates failover runbooks per wave — reduces DR planning from weeks to days
Data Masking Agent | Pre-migration | +1-2% on compliance | Auto-scans PII in 4273 servers — GDPR/PCI compliance for PG&E customer data
Rollback Decision Agent | Execution | Risk reduction | AI go/no-go decision per wave cutover — reduces human error on critical decisions
App Classifier (91% ML) | Discovery | +2-3% on 6R classification | 91% accuracy classifying 415 apps — reduces manual classification by 90%
Duration Predictor (ML) | Planning | Better scheduling | Predicts per-wave duration — enables realistic project scheduling for 7 waves
Anomaly Detector (ML) | Post-migration | Risk reduction | Catches performance anomalies post-migration before users report issues
Terraform Gen Service | Build | +5% on IaC | Auto-generates HCL from discovery — neither Matilda nor Concierto has this
Guardrails Engine | Execution | Cost protection | Prevents runaway cloud spending during migration — $500 budget cap per action
EXECUTIVE BOTTOM LINE: Agentic AI Differentiation
CloudMigrate.store is the ONLY platform with true Agentic AI architecture:
10 autonomous Claude-powered agents that reason, plan, and execute migration tasks
4 ML models trained on migration data (91% app classification accuracy)
8 dedicated MCP microservices for specialized migration functions
Guardrails engine preventing runaway costs and unsafe operations
Matilda Cloud: Zero AI agents. Rule-based automation only. Good execution engine but no intelligence layer.
Concierto Migrate: AI in discovery (CloudIgnite) + modernization (5000+ rules) but NOT agentic — no autonomous agents.
The Agentic AI layer is what enables CloudMigrate's +4% over Matilda and +1% over Concierto:
AI agents make context-aware decisions (not just follow rules)
ML models predict outcomes (not just report current state)
MCP services provide specialized intelligence (not just generic APIs)
Guardrails ensure safety (neither Matilda nor Concierto has this)
For PG&E (415 apps, 4273 servers, NERC CIP): The IAM Agent, Compliance Agent, and Data Masking Agent
are particularly valuable for a regulated utility handling customer energy data.