## AI Assumptions
AI Acceleration Factors - How Traditional vs AI Days Are Calculated
Yellow cells = user-adjustable inputs ¦ Blue cells = auto-calculated formulas
Section A: AI Acceleration Multipliers by Activity Type
Activity Category | AI Acceleration Factor | Explanation / How AI Reduces Time | Traditional Effort Driver | AI Approach | Residual Manual %
Infrastructure Discovery | 30% | 70% savings. Concierto CloudIgnite is very strong — agentless AI-powered discovery (agentless + agent-based), covers VMware/Hyper-V/physical well. Lacks unified multi-cloud single-pane — separate scans per platform need manual merging. [Ref: Gartner MQ 2024 + Concierto product benchmark] | Manual server-by-server inventory, spreadsheet reconciliation, app owner interviews | Concierto agentless discovery + agent-based deep scan; manual merge needed for multi-cloud consolidated view | 32%
App Dependency Mapping | 35% | 65% savings. Concierto CloudIgnite AI-powered dependency mapping is strong + process-level analysis. Good for standard dependencies but limited AI-augmented pattern detection for complex cross-app chains. [Ref: Gartner 2024 - Concierto rated strong in discovery] | Manual interviews with app owners, network trace analysis, cross-team dependency workshops | Concierto network flow + process analysis; manual validation still needed for 35-40% of dependencies | 38%
Database Analysis | 38% | 62% savings. Concierto has no dedicated DB module — relies on standard SCT/DMA/Azure DMA for schema analysis. Standard tool integration — no additional AI-assisted fix layer beyond what SCT provides. [Ref: AWS SCT docs + Concierto integration docs] | Manual schema review, stored proc analysis, compatibility matrix building | Concierto wraps SCT/DMA scanning; standard compatibility reports without AI-suggested fixes for unconverted objects | 35%
Performance Baseline | 32% | 70% savings. Concierto collects performance metrics via APIs — similar to industry standard. CloudWatch/Azure Monitor integration is well-implemented. [Ref: AWS CloudWatch + Concierto perf module] | Manual metric collection, spreadsheet charting, baseline documentation, anomaly identification | Concierto API-driven metric collection + baseline computation; human review for threshold decisions | 30%
Compliance & Security | 52% | 50% savings. Concierto has basic compliance checking but no dedicated compliance microservice. NERC CIP evidence collection is largely manual regardless of tool. [Ref: NERC CIP requirements + Concierto docs] | Manual control review, evidence collection, policy mapping, regulatory documentation | Concierto basic compliance rules + gap flagging; manual evidence collection and NERC CIP sign-off | 50%
License Analysis | 38% | 58% savings. Concierto has license tracking module but limited AI-driven BYOL eligibility analysis. Standard CMDB-driven approach. [Ref: Flexera 2024 + Concierto license module] | Manual license inventory, vendor contract review, BYOL eligibility assessment | Concierto CMDB-driven license inventory; manual for vendor contract interpretation and BYOL negotiation | 42%
TCO / Cost Modeling | 25% | 75% savings. Concierto CloudIgnite has excellent multi-cloud TCO — native AWS/Azure/GCP with cloud pricing integration. Covers AWS + Azure but requires separate runs per cloud — no single multi-cloud comparison view. [Ref: AWS Pricing + Concierto cost module] | Manual spreadsheet modeling, vendor quote gathering, assumption documentation | Concierto auto-generated TCO per cloud platform; manual consolidation for multi-cloud comparison | 30%
Wave Planning | 33% | 67% savings. Concierto CloudIgnite intelligent wave planning with risk assessment is strong data + configurable rules. Functional but rule-based rather than AI-optimized — adequate for most scenarios. [Ref: McKinsey 2023 + Concierto wave planner] | Manual dependency review, stakeholder negotiation, change window scheduling | Concierto rule-based wave grouping from dependency data; manual for stakeholder alignment and change windows | 38%
Landing Zone Design | 40% | 65% savings (validation only — PG&E provides LZ). Concierto has LZ templates but limited auto-validation capability. [Ref: AWS Landing Zone Accelerator + Concierto docs] | Manual architecture review, compliance gap analysis, design documentation | Concierto template-based LZ design + manual readiness validation; limited automated gap detection | 35%
Terraform/IaC Generation | 45% | 55% savings. Concierto has NO native IaC/Terraform generation — external workflows required/CloudFormation templates from discovery. Good template library but less dynamic auto-population from live inventory vs purpose-built IaC generators. [Ref: HashiCorp 2024 + Concierto IaC module] | Manual HCL writing, module development, testing, review iterations | Concierto Terraform template generation; manual customization still significant for complex modules | 30%
Container Artifact Gen | 33% | 67% savings. Concierto Modernize: 5000+ rule scanning, container/microservices transformation — STRONG support — basic Dockerfile templates but no AI source-code analysis for runtime dependency detection. Containerization is not Concierto core strength. [Ref: CNCF 2024 + Concierto product scope] | Manual Dockerfile creation, K8s manifest writing, Helm chart development | Concierto basic Dockerfile templates; manual creation still needed for most non-trivial containerization | 45%
Framework Upgrades | 48% | 52% savings. Concierto Modernize: Autonomous agents for code transformation — better than generic tools assistance — this is outside Concierto platform scope. Standard developer tooling (IDE + Copilot) applies. [Ref: Concierto product scope — migration automation, not code modernization] | Manual code refactoring, dependency updates, regression fixing, build testing | No Concierto capability here; standard IDE + Copilot assist for code changes | 58%
Middleware Migration | 50% | 50% savings. Concierto Modernize: 5000+ deterministic rules for automated code refactoring support — basic config export for common middleware but no deep plugin compatibility analysis. [Ref: Concierto product scope] | Manual config extraction, version migration, plugin compatibility testing | Concierto basic middleware config export; manual migration for custom plugins and job scheduling | 58%
Schema Conversion | 42% | 60% savings. Concierto wraps standard SCT/DMA — no additional AI-assisted fix layer. Complex stored proc conversion remains fully manual DBA work. [Ref: AWS SCT tiers + Concierto DB module] | Manual stored proc rewriting, trigger conversion, cross-DB reference resolution | Concierto wraps SCT auto-conversion; no AI pattern matching for unconverted objects — manual DBA rewrite | 40%
Rehearsal / Dry Run | 38% | 62% savings. Concierto CloudMach: Automated testing and validation at each stage — better than checklist execution. Good orchestration but limited automated outcome validation — manual checklist-based verification. [Ref: Concierto execution module] | Manual rehearsal execution, validation checklist, defect logging, re-planning | Concierto orchestrated rehearsal execution; manual validation checklist and outcome assessment | 43%
Rehost Execution | 30% | 70% savings. Concierto CloudMach CORE STRENGTH: 1000+ VMs/month, zero-downtime cutover, 99.8% success rate automation with MGN/ASR orchestration. Cutover workflow well-integrated. One of Concierto best features. [Ref: AWS MGN + Gartner + Concierto rehost module] | Manual server migration, replication monitoring, cutover coordination, post-migration validation | Concierto MGN/ASR orchestration + cutover workflow; strong execution automation — manual for rollback decisions | 38%
Replatform Execution | 40% | 60% savings. Concierto CloudMach: Continuous source-target sync during replatform — better than basic tools workflows (OS upgrade scripts) but less automated pre/post validation than purpose-built platforms. [Ref: Industry avg + Concierto replatform module] | Manual OS patching, DB upgrade, compatibility testing, validation | Concierto scripted OS/DB upgrades; manual pre/post validation and compatibility testing | 45%
Containerize Execution | 40% | 60% savings. Concierto Modernize + CloudMach: Integrated container transformation and deployment execution — relies on external CI/CD (Jenkins/GitHub Actions). No pre-configured pipeline from artifact generation. [Ref: CNCF 2024 + Concierto product scope] | Manual Docker build, push, K8s deploy, smoke test, config tuning | Concierto orchestrates external CI/CD pipeline; manual pipeline setup and config required | 48%
FR Testing (60%) | 52% | 48% savings. Concierto CloudMach has built-in validation but no AI test case generation capability. Testing relies on external test automation frameworks (Selenium, Cypress). No AI-assisted test case generation. [Ref: Forrester TEI + Concierto product scope] | Manual test case design, execution, defect logging, root cause analysis | No Concierto test generation; standard test automation frameworks — Selenium/Cypress execution only | 55%
NFR Testing (30%) | 55% | 45% savings. Concierto has no perf test generation — relies on standard JMeter/Gatling. Relies on external JMeter/Gatling. No auto-generated load scripts from traffic patterns. [Ref: Gartner + Concierto product scope] | Manual JMeter/Gatling scripting, scenario design, result analysis, bottleneck identification | No Concierto perf test support; standard JMeter/Gatling with manual scripting | 53%
Right-Sizing | 28% | 72% savings. Concierto Maximize: AI-powered real-time cost optimization — STRONG MODULE tools (Compute Optimizer, Azure Advisor). Similar to industry standard — adds management layer. [Ref: AWS Compute Optimizer + Concierto optimization module] | Manual CloudWatch analysis, sizing spreadsheets, vendor benchmarking | Concierto wraps Compute Optimizer/Azure Advisor; cloud-native tools do the heavy lifting | 30%
Monitoring Setup | 38% | 62% savings. Concierto Manage: Single-pane-of-glass across AWS/Azure/GCP/on-prem — strong deployment but limited auto-generation from discovery metadata. Standard CloudWatch/Azure Monitor setup required. [Ref: Datadog/Grafana + Concierto docs] | Manual dashboard creation, alert configuration, SLO definition, escalation setup | Concierto basic monitoring templates; manual dashboard and alert configuration still significant | 45%
Vuln Discovery Scan | 42% | 58% savings. Concierto has NO vuln scanning module — separate Nessus/Qualys required platform — requires separate Nessus/Qualys integration. No migration-context-aware CVSS triage. [Ref: Tenable/Qualys + Concierto product scope] | Manual scan scheduling, CSV export, CVSS triage, false positive validation | Concierto does not include vuln scanning; requires separate Nessus/Qualys with manual triage | 38%
Vuln Remediation Planning | 50% | 50% savings. Concierto has NO remediation planning — separate ServiceNow required planning. Separate ServiceNow/JIRA workflows required. No migration-aware patch scheduling. [Ref: ServiceNow VR + Concierto product scope] | Manual CVE-to-patch mapping, dependency analysis, change request creation, CAB scheduling | No Concierto vuln remediation; separate ServiceNow workflows with manual patch-migration coordination | 48%
Vuln Patch Execution | 50% | 50% savings. Concierto has NO patch management — separate SSM/Ansible required — requires separate SSM/Ansible. No auto-generated compliance evidence trail. [Ref: AWS SSM + Concierto product scope] | Manual patch deployment, snapshot creation, reboot coordination, compliance evidence | No Concierto patching capability; standard SSM/Ansible with manual compliance evidence collection | 48%
Vuln Continuous Monitoring | 48% | 52% savings. Concierto has NO continuous vuln monitoring — separate tools required monitoring. Requires separate Nessus/Qualys scheduled scans + manual JIRA ticketing. [Ref: Industry avg + Concierto product scope] | Periodic manual scans, spreadsheet tracking, manual ticket creation, SLA monitoring | No Concierto continuous vuln monitoring; separate tool integration with manual ticket creation | 45%
Section B: Scale Factors (Server/App Volume Impact on Duration)
Factor | Value | Description
Total Applications | 415 | From PG&E landscape analysis
Total Servers | 4273 | Across all platforms
AWS Apps | 107 | Target platform count
Azure Apps | 145 | Target platform count
Azure Local Apps | 110 | Target platform count
HyperV Apps | 20 | Target platform count
Containerize Apps | 159 | Journey type count
Lift-and-Shift Apps | 179 | Journey type count
Retire Apps | 24 | Journey type count
Base Days per Discovery (per 100 servers) | 5 | Industry benchmark: 5 days per 100 servers manual
Base Days per App (Dependency Map) | 0.3 | Industry benchmark: ~0.3 days per app manual
Base Days per App (Wave Planning) | 0.2 | Industry benchmark: ~0.2 days per app manual
Base Days per App (Rehost Execution) | 0.5 | Industry benchmark: ~0.5 days per app manual
Base Days per App (Containerize) | 1.2 | Industry benchmark: ~1.2 days per app manual
Section C: How Duration Is Calculated (Formula Methodology)
TRADITIONAL DAYS = Base Days per unit x Volume (apps or servers) x Complexity multiplier
Example: Infrastructure Discovery = (4273 servers / 100) x 5 base days = ~214 person-days, split across 3 clouds
Example: App Dependency Mapping = 415 apps x 0.3 days/app = ~125 person-days, split across 3 clouds
AI-ACCELERATED DAYS = Traditional Days x AI Acceleration Factor (from Section A)
Example: Discovery Traditional=20 days (AWS share), AI Factor=20% => AI Days = 20 x 0.20 = 4 days
Example: Containerize Trad=25 days, AI Factor=20% => AI Days = 25 x 0.20 = 5 days
TIME SAVED % = (Traditional - AI) / Traditional x 100
Example: (20 - 4) / 20 x 100 = 80% time saved on discovery
KEY PRINCIPLES (Industry-Validated):
1. Discovery & data-heavy activities: 60-70% savings (Gartner 2024: discovery tools reduce effort 50-70%)
2. IaC / code generation: 60-70% savings (HashiCorp: IaC reduces provisioning 60-75%)
3. Execution (Rehost/Replatform): 55-60% savings (AWS MGN automates replication, cutover manual)
4. Code-change activities (Framework, Middleware): 45% savings (GitHub Copilot: 30-50% faster)
5. Testing (FR/NFR): 50% savings (Forrester: test automation reduces execution 40-60%)
6. Compliance/NERC CIP: 50% savings (regulatory evidence collection still manual-heavy)
7. Vulnerability Management: 55-65% savings (scanning automated, triage/patching semi-manual)
OVERALL BLENDED SAVINGS: ~61% with Concierto Migrate (stronger in rehost/modernize, weaker in vuln/IaC/testing) (Industry std: ~59% ¦ McKinsey benchmark: 40-60%)
Concierto is slightly above industry standard (~61%) — very strong rehost + modernize, weak in vuln/IaC/testing — strong in discovery/execution, less differentiated in AI-augmented analysis
INDUSTRY REFERENCES:
- McKinsey (2023): AI accelerates cloud migration by 30-50% overall
- Gartner Magic Quadrant Migration Tools (2024): 50-70% for discovery, 45-65% for execution
- AWS Well-Architected Migration Lens: MGN replication automated, cutover manual
- Forrester TEI: Migration platforms show 40-60% efficiency gains
- Infosys Cobalt benchmarks: 30-40% acceleration on traditional, 50-65% with AI augmentation
- AWS SCT: Auto-conversion rate 60-80% depending on DB complexity tier
- HashiCorp State of Cloud (2024): IaC reduces provisioning time 60-75%
- CNCF Survey (2024): Containerization deployment 50-60% automatable
ADJUST: Change yellow cells in Section A to model scenarios:
Conservative: Set all factors to 0.55-0.60 (40-45% savings) - defensible for skeptical stakeholders
Moderate: Current values (45-70% savings) - industry-aligned, realistic for AI-augmented migration
Aggressive: Set data-processing factors to 0.20-0.25 (75-80% savings) - requires mature tooling + experienced team

## Migration Activities
PG&E Cloud Migration - Activities, Duration & AI Accelerator Savings
415 Apps ¦ 4,273 Servers ¦ All durations formula-driven from AI Assumptions tab (yellow = input, blue = formula)
CIS CLD (AWS/Azure) ¦ CIS EIT (Azure Local/HyperV) ¦ ADM (Containerize/Framework) ¦ IQE (Testing) ¦ CyberSec (Security)
Phase | Activity | Team | Description | AWS Trad (Days) | AWS AI (Days) | AWS Saved % | Azure Trad (Days) | Azure AI (Days) | Azure Saved % | AzLocal/HV Trad (Days) | AzLocal/HV AI (Days) | AzLocal/HV Saved % | Concierto Migrate Accelerator Activity | AI Factor Ref | How Calculated
Phase 1: Discovery & Assessment [COMPLETED]
| Infrastructure Discovery (4273 servers) [DONE] | CIS CLD + EIT | COMPLETED - Scan all VMs, physical, DBs, network | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Discovery: Agentless + agent-based scan, VMware/Hyper-V/physical inventory | Infrastructure Discovery | 4273 svrs / 100 x 5d = 214 total, split by platform
| App Dependency Mapping (415 apps) [DONE] | CIS CLD + ADM | COMPLETED - Map inter-app dependencies, all 415 apps | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Dependency: Network flow + process analysis; manual validation for 35-40% of deps | App Dependency Mapping | 415 apps x 0.3d = 125 total, split by platform
| Database Schema Analysis [DONE] | CIS CLD | COMPLETED - Analyze schemas, stored procs, compatibility | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto DB Module: Wraps AWS SCT/Azure DMA for schema analysis; standard reports | Database Analysis | DB-heavy apps analyzed per platform
| Performance Baseline [DONE] | CIS CLD + EIT | COMPLETED - Capture CPU, mem, IOPS baselines per server | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Perf: API-driven metric collection via CloudWatch/Azure Monitor | Performance Baseline | 4273 servers, automated metric collection
| Compliance & Security Audit [DONE] | CyberSec | COMPLETED - PG&E compliance (NERC CIP), security gaps | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Compliance: Basic rule checking + gap flagging; no dedicated compliance service | Compliance & Security | Regulated utility - higher residual manual
| License Analysis (BYOL) [DONE] | CIS CLD | COMPLETED - Audit Oracle, SQL Server, SAP for BYOL | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto License: CMDB-driven inventory; manual BYOL analysis required | License Analysis | CMDB-driven license correlation
| TCO / Cost Modeling [DONE] | CIS CLD | COMPLETED - Build TCO for each target platform | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Cost: TCO per cloud; manual consolidation for multi-cloud comparison | TCO / Cost Modeling | Auto-generated from discovery data
| Journey Assignment & 6R [DONE] | CIS CLD + ADM | COMPLETED - Classify 415 apps into journeys | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto Rules: Rule-based 6R classification; less AI-augmented than purpose-built platforms | Wave Planning | AI classifies based on app profile
| Vulnerability Baseline Scan (4273 servers) [DONE] | CyberSec | COMPLETED - Full vuln scan of all source servers pre-migration, CVSS categorization | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto: No vuln scanning — separate Nessus/Qualys required | Vuln Discovery Scan | 4273 servers, CVSS-prioritized report
| Vuln Remediation Plan (Pre-Migration) [DONE] | CyberSec | COMPLETED - Prioritize critical/high CVEs for remediation before migration | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | Concierto: No remediation planning — separate ServiceNow required | Vuln Remediation Planning | Fix critical CVEs before migrating workloads
Phase 2: Planning & Design
| Wave Planning (7 waves) | CIS CLD | Group 415 apps into 7 waves | 12 |  |  | 12 |  |  | 12 |  |  | Concierto Wave: Rule-based wave grouping from dependency data; configurable rules engine | Wave Planning | 415 apps x 0.2d = 83 total, graph optimization
| LZ Validation - AWS (PG&E Provided) | CIS CLD | Validate PG&E-built VPC/subnets/SG/IAM | 3 |  |  | 0 | 0 |  | 0 | 0 |  | Concierto LZ: Template-based design; limited automated validation | Landing Zone Design | PG&E provides LZ; Infosys validates readiness
| LZ Validation - Azure (PG&E Provided) | CIS CLD | Validate PG&E-built VNet/NSG/RBAC | 0 | 0 |  | 3 |  |  | 0 | 0 |  | Concierto LZ: Template-based design; limited automated validation | Landing Zone Design | PG&E provides LZ; Infosys validates readiness
| LZ Validation - AzLocal/HV (PG&E Provided) | CIS EIT | Validate PG&E-built Azure Local/HyperV | 0 | 0 |  | 0 | 0 |  | 5 |  |  | Concierto LZ: Basic cluster template; manual capacity validation | Landing Zone Design | PG&E provides infra; EIT validates config
| App-Level IaC Generation | CIS CLD + EIT | Generate app-level Terraform (SG, LB, DNS) | 10 |  |  | 10 |  |  | 12 |  |  | Concierto IaC: Terraform template generation; manual customization still significant | Terraform/IaC Generation | App-level only; foundational IaC by PG&E
| DB Migration Planning (DMS/DMA) | CIS CLD | Schema conversion, CDC strategy | 10 |  |  | 10 |  |  | 12 |  |  | Concierto DB: DMS task design wrapping SCT; manual CDC strategy | Database Analysis | DMS task planning per DB target
| Containerization Architecture | ADM | Docker/K8s design for 159 apps | 15 |  |  | 15 |  |  | 15 |  |  | Concierto Modernize: 5000+ rule code scanning, container/microservices transformation, AI-driven arch recommendations | Container Artifact Gen | 159 containerize apps, arch design
| Rollback & DR Strategy | CIS CLD | Rollback procedures per wave, DR plan | 8 |  |  | 8 |  |  | 8 |  |  | Concierto Rollback: Workflow-based rollback; manual DR checklist | Compliance & Security | Template-based + manual review
| Business Impact Assessment | CIS CLD | Downtime cost per app tier | 5 |  |  | 5 |  |  | 5 |  |  | Concierto Cost: Basic downtime estimate; manual impact assessment | TCO / Cost Modeling | AI computes from app metadata
Phase 3: Build & Prepare
| App-Level Provisioning - AWS | CIS CLD | Deploy app SGs, target groups, DNS in PG&E LZ | 5 |  |  | 0 | 0 |  | 0 | 0 |  | Concierto Executor: Terraform apply orchestration; manual for complex configs | Terraform/IaC Generation | PG&E LZ ready; app-level config only
| App-Level Provisioning - Azure | CIS CLD | Deploy app NSGs, LB rules, DNS in PG&E LZ | 0 | 0 |  | 5 |  |  | 0 | 0 |  | Concierto Executor: Terraform apply orchestration; manual for complex configs | Terraform/IaC Generation | PG&E LZ ready; app-level config only
| Workload Onboarding - AzLocal/HV | CIS EIT | Onboard workloads to PG&E-built clusters | 0 | 0 |  | 0 | 0 |  | 10 |  |  | Concierto Executor: Basic migration orchestration; manual placement optimization | Middleware Migration | PG&E provides infra; EIT onboards apps
| Container Artifact Gen (159 apps) | ADM | Dockerfiles, K8s manifests, Helm charts | 25 |  |  | 25 |  |  | 25 |  |  | Concierto: Basic Dockerfile templates; no AI source-code analysis | Container Artifact Gen | 159 apps x AI source analysis
| Framework Upgrades (.Net/Java) | ADM | .Net/Java upgrades for containerization | 20 |  |  | 20 |  |  | 20 |  |  | Concierto Modernize: Autonomous agents for code transformation, .NET/Java/mainframe framework upgrades | Framework Upgrades | Semi-auto, 40% residual manual
| Middleware Upgrades & Jobs | ADM | Middleware versions, batch job migration | 15 |  |  | 15 |  |  | 15 |  |  | Concierto Modernize: Automated code refactoring for middleware; 5000+ deterministic rules | Middleware Migration | Config extraction + manual verification
| DB Schema Conversion | CIS CLD | Convert stored procs, triggers, functions | 20 |  |  | 20 |  |  | 22 |  |  | Concierto: Standard SCT integration only; no AI-assisted fix for unconverted objects | Schema Conversion | SCT auto-converts 80%, AI fixes rest
| Migration Rehearsal (Dry Run) | CIS CLD + ADM | Full rehearsal per wave in non-prod | 15 |  |  | 15 |  |  | 18 |  |  | Concierto CloudMach: Automated testing and validation at each migration stage | Rehearsal / Dry Run | AI orchestrates + validates outcomes
| Integration Testing | IQE | Validate connectivity, APIs, data integrity | 15 |  |  | 15 |  |  | 18 |  |  | Concierto CloudMach: Built-in automated validation at each stage; complements manual testing | NFR Testing (30%) | IQE functional validation post-rehearsal
| Security Validation | CyberSec | Vulnerability scans, compliance per wave | 8 |  |  | 8 |  |  | 10 |  |  | Concierto: No native security validation — relies on 3rd-party tools | Compliance & Security | PG&E NERC CIP requirements
| Pre-Migration Patch Execution | CyberSec | Patch critical/high CVEs on source before cutover | 12 |  |  | 12 |  |  | 15 |  |  | Concierto: No patch management — separate SSM/Ansible + manual NERC CIP evidence | Vuln Patch Execution | Must-fix before migration per PG&E policy
Phase 4: Migration Execution
| Wave 1: Pilot (10-15 apps) | CIS CLD | Pilot batch across all platforms | 8 |  |  | 8 |  |  | 10 |  |  | Concierto CloudMach: Automated migration factory with continuous sync; strong pilot execution | Rehost Execution | Validate patterns before scale
| Rehost / Lift-and-Shift (179 apps) | CIS CLD + EIT | V->V, P->V, HyperVisor-Replace | 40 |  |  | 45 |  |  | 50 |  |  | Concierto CloudMach: 1000+ VMs/month throughput, zero-downtime cutover, 99.8% success rate — CORE STRENGTH | Rehost Execution | 179 apps x 0.5d = ~90 total, split by platform
| Replatform (OS/DB Upgrade) | CIS CLD | OS upgrades, DB upgrades during migration | 25 |  |  | 25 |  |  | 28 |  |  | Concierto CloudMach: Continuous source-target sync during replatform; automated validation | Replatform Execution | CIS CLD-led, scripted upgrades
| Containerize Execution (159 apps) | ADM | Docker build, push, EKS/AKS deploy | 35 |  |  | 35 |  |  | 35 |  |  | Concierto Modernize: Container transformation + deployment; integrated with CloudMach execution | Containerize Execution | 159 apps x 1.2d = ~191 total, split
| Framework Replace (5 apps) | ADM | .Net/Java framework replacement | 8 |  |  | 8 |  |  | 8 |  |  | Concierto Modernize: AI-driven framework transformation with autonomous agents | Framework Upgrades | 5 apps, high complexity per app
| Retire (24 apps) | CIS CLD | Decommission retired applications | 5 |  |  | 5 |  |  | 5 |  |  | Concierto CloudMach: Post-migration validation before decommission; rollback capability | License Analysis | Dependency check + decommission
| Database Migration (DMS/CDC) | CIS CLD | CDC replication and cutover | 20 |  |  | 20 |  |  | 22 |  |  | Concierto CloudMach: Continuous sync for DB migration; automated cutover scheduling | Schema Conversion | DMS tasks across all DB targets
| DNS Cutover & Traffic Shift | CIS CLD | Switch DNS per wave, validate | 5 |  |  | 5 |  |  | 5 |  |  | Concierto CloudMach: Zero-downtime cutover with minutes of business impact | Rehost Execution | Orchestrated cutover
| Rollback Execution | CIS CLD | Rollback for failed migrations | 5 |  |  | 5 |  |  | 5 |  |  | Concierto CloudMach: Built-in rollback capability for safe return to source | Rehost Execution | Pre-built rollback scripts
| Post-Migration Vuln Scan (per wave) | CyberSec | Scan migrated workloads for new vulns introduced during migration | 10 |  |  | 10 |  |  | 12 |  |  | Concierto: No post-migration vuln scanning — separate tools required | Vuln Discovery Scan | Compare against pre-migration baseline
| Vuln Remediation - Migrated Targets | CyberSec | Patch any new vulns found on target cloud instances | 8 |  |  | 8 |  |  | 10 |  |  | Concierto: No patch management — separate SSM/Ansible required | Vuln Patch Execution | New vulns from migration or cloud-specific CVEs
Phase 4a: Testing (IQE-Led)
| FR Testing - Rearchitect (60%) | IQE | Full FR for 159 containerized apps @ 60% | 45 |  |  | 45 |  |  | 45 |  |  | Concierto CloudMach: Automated testing at each stage; no AI test case generation | FR Testing (60%) | 159 apps x 3d x 60% effort = per platform
| FR Testing - Framework Replace (40%) | IQE | Targeted FR for 5 framework-replaced apps | 8 |  |  | 8 |  |  | 8 |  |  | Concierto: No targeted test generation — relies on standard test frameworks | FR Testing (60%) | 5 apps x 5d x 40% effort
| NFR Testing - Replatform (30%) | IQE | Perf/load/stress for replatformed apps | 20 |  |  | 20 |  |  | 22 |  |  | Concierto: No perf test generation — relies on standard JMeter/Gatling | NFR Testing (30%) | Full perf baseline validation
| NFR Testing - Replatform Lite (20%) | IQE | Basic perf for lift-and-shift apps | 12 |  |  | 12 |  |  | 14 |  |  | Concierto: No smoke test automation — standard tools | NFR Testing (30%) | Smoke + basic perf validation
| Security Testing (Pen Test) | IQE + CyberSec | Pen testing for tier-1 post-migration | 10 |  |  | 10 |  |  | 10 |  |  | Concierto: No security testing — separate pen test tools needed | NFR Testing (30%) | PG&E mandatory for critical apps
| UAT Coordination | IQE | Coordinate UAT with business teams | 10 |  |  | 10 |  |  | 10 |  |  | Concierto: No UAT module — standard JIRA/ALM | NFR Testing (30%) | IQE facilitates, business executes
Phase 5: Post-Migration Optimize
| Right-Sizing (4273 servers) | CIS CLD | Optimize instance sizes from usage data | 12 |  |  | 12 |  |  | 12 |  |  | Concierto Maximize: AI-powered real-time cost optimization and forecasting across multi-cloud | Right-Sizing | AI from 30-day usage analysis
| Cost Optimization (FinOps) | CIS CLD | Reservations, spot, savings plans | 8 |  |  | 8 |  |  | 8 |  |  | Concierto Maximize: Real-time cost optimization, RI/SP recommendations, forecasting — STRONG MODULE | TCO / Cost Modeling | AI identifies savings opportunities
| Monitoring & Alerting Setup | CIS CLD + EIT | CloudWatch/Azure Monitor/Grafana | 8 |  |  | 8 |  |  | 10 |  |  | Concierto Manage: Single-pane-of-glass operations across AWS/Azure/GCP/on-prem | Monitoring Setup | Template + PG&E custom alerts
| Documentation & Handoff | All Teams | Runbooks, architecture docs, KT | 10 |  |  | 10 |  |  | 10 |  |  | Concierto Manage: Unified operations view; limited auto-documentation | Compliance & Security | AI generates draft docs from migration data
| Decommission Source Infra | CIS CLD + EIT | Shut down on-prem after validation | 10 |  |  | 10 |  |  | 10 |  |  | Concierto CloudMach: Post-migration validation + rollback capability before decommission | License Analysis | Staged per wave after 30-day soak
| Continuous Vuln Monitoring Setup | CyberSec | Configure ongoing vuln scanning, auto-ticketing for new CVEs | 8 |  |  | 8 |  |  | 10 |  |  | Concierto: No vuln management — separate Nessus/Qualys + manual ticketing required | Vuln Continuous Monitoring | Ongoing post-migration vulnerability hygiene
| Vuln Compliance Dashboard | CyberSec | Build vuln posture dashboard for PG&E exec reporting | 5 |  |  | 5 |  |  | 5 |  |  | Concierto: No vuln dashboard — separate reporting tools needed | Vuln Continuous Monitoring | PG&E exec visibility into security posture
TOTAL
AI Accelerator Savings Summary
| Platform | Apps | Servers | Traditional Days | AI Days | Days Saved | % Saved | Months Saved
| AWS | 107 | 719
| Azure | 145 | 852
| Azure Local/HyperV | 130 | 2702

## Cost Estimation
PG&E Migration Cost - 4-Team Model, 2-Year Projection
415 Apps ¦ 4,273 Servers ¦ Yellow = adjustable input ¦ All costs formula-driven
Section A: Team Role Rate Card
Team | Role | Hourly ($) | Daily ($) (8 hrs) | Monthly ($) (22 days) | FTE Count | Monthly Cost ($) | Annual Cost ($) | Location
CIS CLD | Cloud Migration Lead | 180 |  |  | 1 |  |  | Onshore
CIS CLD | Sr. Migration Engineer | 150 |  |  | 4 |  |  | Offshore
CIS CLD | Migration Engineer | 100 |  |  | 6 |  |  | Offshore
CIS CLD | DB Migration Specialist | 160 |  |  | 2 |  |  | Offshore
CIS CLD | DevOps / SRE Engineer | 140 |  |  | 2 |  |  | Offshore
CIS CLD | Network Engineer (App-Level) | 125 |  |  | 0 |  |  | Offshore
CIS CLD | Project Manager | 155 |  |  | 1 |  |  | Onshore
CIS EIT | Azure Local / HyperV Lead | 170 |  |  | 1 |  |  | Onshore
CIS EIT | Infrastructure Engineer | 130 |  |  | 3 |  |  | Offshore
CIS EIT | Network Engineer (App-Level) | 125 |  |  | 0 |  |  | Offshore
ADM | App Modernization Lead | 175 |  |  | 1 |  |  | Onshore
ADM | Sr. App Developer | 145 |  |  | 4 |  |  | Offshore
ADM | App Developer | 100 |  |  | 6 |  |  | Offshore
ADM | Middleware Engineer | 135 |  |  | 2 |  |  | Offshore
ADM | DevOps (K8s) | 140 |  |  | 2 |  |  | Offshore
IQE | Test Lead | 150 |  |  | 1 |  |  | Onshore
IQE | Sr. Test Engineer (FR) | 120 |  |  | 3 |  |  | Offshore
IQE | Perf Test Engineer (NFR) | 130 |  |  | 2 |  |  | Offshore
IQE | Security Test Engineer | 140 |  |  | 1 |  |  | Offshore
IQE | Test Automation Engineer | 125 |  |  | 2 |  |  | Offshore
CyberSec | Security Analyst | 155 |  |  | 1 |  |  | Onshore
CyberSec | Vuln Mgmt Engineer | 140 |  |  | 2 |  |  | Offshore
FinOps | FinOps Analyst | 130 |  |  | 1 |  |  | Offshore
TOTAL ALL TEAMS
Section B: Phase-Based Cost (Duration from Migration Activities tab)
Phase | Primary Team | Trad Days | AI Days | Team FTEs | Blended Daily Rate ($) | Traditional Cost ($) | AI Cost ($) | Savings ($) | Savings % | Cloud Infra $/Month | Phase Total AI ($)
Discovery & Assessment [COMPLETED] | CIS CLD + EIT | 0 | 0 | 0 | 1050 |  |  |  |  | 0
Planning & Design | CIS CLD + ADM | 72 | 28 | 16 | 1100 |  |  |  |  | 500
Build & Prepare | All Teams | 115 | 45 | 22 | 1050 |  |  |  |  | 1000
Migration Execution - Rehost | CIS CLD + EIT | 90 | 35 | 16 | 1050 |  |  |  |  | 0
Migration Execution - Containerize | ADM | 48 | 19 | 17 | 1000 |  |  |  |  | 0
Migration Execution - Other | CIS CLD | 33 | 13 | 10 | 1100 |  |  |  |  | 0
Testing - FR (Rearchitect 60%) | IQE | 56 | 22 | 11 | 1000 |  |  |  |  | 0
Testing - NFR (Replatform 30%) | IQE | 35 | 14 | 8 | 1050 |  |  |  |  | 0
Testing - Security & UAT | IQE + CyberSec | 22 | 9 | 7 | 1100 |  |  |  |  | 0
Vulnerability Management (All Phases) | CyberSec | 72 | 28 | 6 | 1100 |  |  |  |  | 0
Post-Migration Optimize | CIS CLD | 52 | 20 | 10 | 1050 |  |  |  |  | 0
TOTAL ALL PHASES
Section C: 2-Year Cost Projection
Cost Category | Year 1 ($) | Year 2 ($) | 2-Year Total ($) | Notes
Migration Labor (AI Accelerated) |  |  |  | Year 2 = 15% steady-state
Cloud Infrastructure (App-Level Only) |  |  |  | PG&E bears LZ/network; app-level only
AI Platform License | 48000 | 48000 |  | Concierto Migrate enterprise
Tooling & 3rd Party | 25000 | 18000 |  | DMS, Terraform Cloud, etc.
Training & Enablement | 20000 | 8000 |  | All 4 teams
CyberSec & Compliance | 35000 | 25000 |  | NERC CIP ongoing
Vuln Mgmt Tooling (Nessus/Qualys) | 18000 | 18000 |  | Annual vuln scanner license
Contingency (12%) |  |  |  | 4273-server migration buffer
GRAND TOTAL (2 YEARS)
Traditional Cost (2 Years - No AI) |  |  |  | Trad labor + 25% Year 2
NET SAVINGS WITH AI |  |  | % Savings

## Executive Summary
PG&E Migration - Executive Summary
Metric | Value
Total Applications | 415
Total Servers | 4273
Traditional Duration - AWS (Days)
AI-Accelerated Duration - AWS (Days)
Time Saved % - AWS
Traditional Migration Cost ($)
AI-Accelerated Cost ($)
2-Year Grand Total ($)
Net Savings vs Traditional ($)
Total FTEs
Key: AI Days = Traditional Days x AI Factor (from AI Assumptions tab)
Change any yellow cell to model different scenarios. All formulas auto-update.

## Executive Dashboard
PG&E Cloud Migration — Executive Dashboard
415 Applications ¦ 4,273 Servers ¦ 5 Teams ¦ AI-Accelerated with Concierto Migrate
Duration Comparison (Days) |  |  |  | KEY METRICS
Platform | Traditional | AI-Accelerated | Days Saved | Applications | 415
AWS (107 apps) |  |  |  | Servers | 4,273
Azure (145 apps) |  |  |  | Target Platforms | AWS + Azure + AzLocal
Azure Local/HV (130 apps) |  |  |  | Teams | CIS CLD + EIT + ADM + IQE
Time Saved (AWS)
Cost Comparison ($) |  |  |  | Cost Savings ($)
Category | Amount ($) |  |  | 2-Year Investment
Traditional Migration (2yr) |  |  |  | Total FTEs
AI-Accelerated (2yr Grand Total)
Net Savings |  |  |  | PG&E Provides | LZ + Network + Infra
|  |  |  | Infosys Delivers | Migration + Modernization
|  |  |  | AI Accelerator | Concierto Migrate
Phase Effort Breakdown (AI Days)
Phase | AI Days
Discovery
Planning
Build
Rehost Exec
Containerize Exec
Other Exec
FR Testing
NFR Testing
Security/UAT
Vuln Mgmt
Optimize
Team FTE Allocation
Team | FTEs
CIS CLD (Rehost/Replatform) | 17
CIS EIT (Azure Local/HyperV) | 5
ADM (Containerize/Framework) | 15
IQE (Testing) | 9
CyberSec (Security/VulnMgmt) | 4
FinOps | 1
App Distribution by Journey |  | Servers by Platform
Journey | Apps | Platform | Servers
Lift-and-Shift | 179 | AWS | 719
Containerize | 159 | Azure | 852
TBD | 31 | Azure Local | 1295
Retire | 24 | HyperV | 356
Framework Replace | 17 | Physical | 164
Fresh Install/Transform | 5 | SaaS/PaaS | 126
|  | TBD | 761

## Team Revenue View
PG&E Migration — Team-wise FTE, Cost & Revenue Breakdown
All values formula-driven from Cost Estimation tab ¦ Yellow = adjustable inputs ¦ Margin % adjustable per team
Section A: Team FTE & Monthly/Annual Cost (from Cost Estimation Rate Card)
Team | Roles | Total FTEs | Avg Hourly Rate ($) | Monthly Cost ($) | Annual Cost ($) | Scope / Responsibility
CIS CLD | Cloud Migration Lead, Sr. Migration Engineers (4), Migration Engineers (6), DB Specialist (2), DevOps (2), PM |  |  |  |  | Rehost, Replatform, DB Migration, Wave Planning on AWS & Azure
CIS EIT | Azure Local/HyperV Lead, Infrastructure Engineers (3) |  |  |  |  | Azure Local & HyperV workload onboarding, cluster validation
ADM | App Modernization Lead, Sr. Developers (4), Developers (6), Middleware (2), DevOps K8s (2) |  |  |  |  | Containerization (159 apps), .Net/Java upgrades, Middleware migration
IQE | Test Lead, SR Test Engineers FR (3), Perf NFR (2), Security (1), Automation (2) |  |  |  |  | FR Testing 60%, NFR Testing 30%, Security Testing, UAT coordination
CyberSec (Vuln Mgmt) | Security Analyst, Vuln Mgmt Engineers (2) |  |  |  |  | Vulnerability scanning, remediation, patching, compliance, NERC CIP
FinOps | FinOps Analyst |  |  |  |  | Cost optimization, RI/SP recommendations
TOTAL
Section B: Team-wise 2-Year Revenue Model (Margin-Adjustable)
Team | FTEs | Year 1 Duration (Mo) | Year 1 Cost ($) | Year 2 Duration (Mo) | Year 2 Cost ($) | 2-Year Total Cost ($) | Margin % (Adjust) | Year 1 Revenue ($) | Year 2 Revenue ($) | 2-Year Revenue ($) | % of Total Revenue
CIS CLD |  | 12 |  | 3 |  |  | 25%
CIS EIT |  | 10 |  | 2 |  |  | 25%
ADM |  | 12 |  | 3 |  |  | 25%
IQE |  | 10 |  | 2 |  |  | 22%
CyberSec (Vuln Mgmt) |  | 12 |  | 6 |  |  | 28%
FinOps |  | 8 |  | 4 |  |  | 20%
TOTAL | [10 empty] | 100%
Section C: Key Revenue Metrics
Total 2-Year Cost (All Teams)
Total 2-Year Revenue (All Teams)
Total Gross Margin ($)
Blended Margin %
Largest Team by Revenue | CIS CLD
Largest Team by FTEs
CyberSec/Vuln Mgmt Revenue Share
Total FTEs Deployed
Avg Revenue per FTE (2yr)

## Tool vs Industry Benchmark
Concierto Migrate vs Industry Standard — Honest Benchmark Comparison
Industry = Generic tooling (AWS Migration Hub + separate SCT + separate Terraform + manual glue) ¦ Concierto = Integrated AI platform
Category | Industry Std Savings % | Concierto Savings % | Delta (Improvement) | Industry Standard Approach (Generic Tools) | Concierto Migrate Advantage (What Our Tool Adds) | Why The Delta (Honest Assessment) | Risk if Overclaimed | Confidence Level | Industry Reference
Infrastructure Discovery | 65% | 72% |  | AWS Migration Hub + Azure Migrate run separately; results in 2 spreadsheets that need manual merging for multi-cloud view | Single-pane discovery across AWS+Azure+AzLocal with unified topology map, 29 component types auto-detected, cross-cloud dependency view | +7%: Unified multi-cloud view eliminates manual merge of separate tool outputs. For 4273 servers across 3 clouds, this saves 2-3 days of reconciliation per discovery cycle | Over-claim if PG&E has heavily air-gapped systems that no tool can reach | High | Gartner 2024 + internal benchmark
App Dependency Mapping | 60% | 65% |  | ServiceNow CMDB + Dynatrace/AppDynamics for runtime deps; still misses 30-40% of dependencies requiring manual app-owner interviews | Network flow tracing + CMDB correlation + AI-powered graph building in one workflow; reduces manual interview rounds from 3 to 1 | +5%: AI graph building catches cross-app patterns that individual tools miss. Conservative delta — dependency mapping is inherently hard regardless of tooling | Dependency mapping accuracy is never 100%; app owner validation always needed | Medium | Gartner 2024
Database Analysis | 65% | 70% |  | AWS SCT + Azure DMA run separately; conversion reports need manual cross-referencing; no AI-assisted fix suggestions | DB Remediation Engine runs SCT + provides AI-assisted fix suggestions for unconverted objects; cross-cloud DB compatibility matrix in one view | +5%: AI-assisted fix suggestions for unconverted stored procs reduce manual effort. SCT still does the heavy lifting — our tool adds the remediation layer | Complex PL/SQL (PG&E Oracle legacy) may still need DBA manual rewrite regardless | Medium-High | AWS SCT docs
TCO / Cost Modeling | 70% | 75% |  | AWS Pricing Calculator + Azure TCO Calculator run separately; manual Excel consolidation for multi-cloud comparison | MCP cloud-cost service generates unified multi-cloud TCO from discovery data with live pricing APIs; auto-comparison across AWS/Azure/AzLocal | +5%: Eliminates manual multi-cloud spreadsheet merging. Auto-links TCO to actual discovered inventory rather than manual input estimates | EDP/RI negotiation and business assumptions still need stakeholder input regardless | High | AWS Pricing + Cobalt
Performance Baseline | 70% | 70% |  | CloudWatch + Azure Monitor + custom scripts; metric collection well-automated by cloud-native tools | Aggregates metrics across all 3 clouds in unified baseline dashboard; but cloud-native tools already do this well individually | 0%: No significant delta. Cloud-native monitoring tools are mature. Our value is unified view, not faster collection | Honest: cloud-native tools are already excellent here | High | AWS CloudWatch
Compliance & Security (NERC CIP) | 50% | 52% |  | Separate compliance scanning tools (Prisma, Prowler) + manual NERC CIP evidence collection; heavily regulated = heavily manual | MCP compliance-framework service + guardrails engine scan against frameworks; but NERC CIP evidence collection and regulatory sign-off remain manual regardless | +2%: Marginal improvement. Compliance for regulated utilities is fundamentally manual-intensive. Our scanning is faster but the bottleneck is human review and regulatory evidence | DO NOT overclaim here. NERC CIP compliance is 70%+ manual — no tool changes this | Low | NERC CIP reqs
Wave Planning | 60% | 65% |  | Manual wave grouping using dependency data from discovery; spreadsheet-based optimization; stakeholder negotiation is the bottleneck | Graph-based wave optimizer uses dependency data + risk scoring + parallel simulation; generates optimal wave plan that would take weeks manually | +5%: Algorithm-optimized wave grouping is genuinely faster than manual spreadsheet analysis. But stakeholder alignment (50% of wave planning effort) is unchanged | Stakeholder negotiation window constraints cannot be automated | Medium-High | McKinsey 2023
Terraform/IaC Generation | 70% | 75% |  | Manual HCL writing using Terraform docs + module registry; separate tool from discovery — no auto-population from discovered inventory | MCP terraform-generator auto-generates HCL from discovery data; app-level resources (SGs, LBs, DNS) pre-populated with actual values from inventory | +5%: Auto-population from discovery data eliminates the manual step of translating inventory into Terraform variables. Module customization and PR review still manual | Complex modules (custom VPC peering, Transit Gateway) still need manual HCL | High | HashiCorp 2024
Container Artifact Gen | 60% | 65% |  | Manual Dockerfile writing + K8s manifest creation; tools like Kompose help but dont analyze source code | AI source-code analysis generates Dockerfiles + K8s manifests + Helm charts tailored to actual app stack; identifies runtime dependencies automatically | +5%: Source code analysis catches dependencies that manual Dockerfile writing misses. But custom configs, multi-stage builds, sidecar patterns still need manual tuning | Non-standard stacks (legacy .NET Framework 4.x, COBOL wrappers) need manual Dockerfiles | Medium | CNCF 2024
Framework Upgrades | 45% | 47% |  | Manual code refactoring with IDE assistance; GitHub Copilot helps but doesnt understand migration context | Upgrade Advisor identifies breaking changes + dependency conflicts in migration context; but actual code changes are still manual developer work | +2%: Marginal. Code refactoring is fundamentally a developer task. Our tool helps with identification, not execution. Honest: AI assist is ~30-50% for code changes (GitHub Copilot data) | DO NOT overclaim. Framework upgrades = developer skill, not tool capability | Low | GitHub Copilot
Middleware Migration | 45% | 47% |  | Manual config extraction + version migration; custom plugins need per-plugin analysis | Config extraction automation + partial middleware mapping; but version differences and custom plugins still need manual migration | +2%: Marginal. Similar to framework upgrades — tool helps with config extraction but the hard part (plugin compat, job scheduling) is manual | Middleware migration complexity varies wildly by product (WebLogic vs Tomcat vs IIS) | Low | Industry avg
Schema Conversion | 60% | 65% |  | AWS SCT auto-converts 60-80% of simple objects; complex PL/SQL needs manual DBA rewrite; no AI-assisted suggestions | DB Remediation Engine wraps SCT + adds AI-suggested fixes for unconverted objects; pattern matching for common PL/SQL-to-PostgreSQL transforms | +5%: AI pattern matching handles common conversion patterns that SCT marks as "manual action needed". Saves DBA time on repetitive patterns, but complex custom PL/SQL still needs expert | PG&E Oracle databases with 10+ years of PL/SQL — complexity may exceed AI pattern library | Medium | AWS SCT tiers
Rehearsal / Dry Run | 55% | 60% |  | Manual rehearsal with runbook; separate monitoring to validate outcomes; post-rehearsal findings tracked in spreadsheet | Orchestrated rehearsal execution with automated outcome validation, gap detection, and finding prioritization in one workflow | +5%: Orchestrated execution + automated validation saves 1-2 days per rehearsal wave vs manual runbook execution. Findings auto-prioritized instead of manual triage | Complex failures still need human root-cause analysis | Medium-High | AWS Playbook
Rehost Execution | 60% | 63% |  | AWS MGN / Azure ASR automate replication (biggest time saver); cutover coordination, DNS switch, validation are manual across separate tools | Unified execution engine orchestrates MGN/ASR replication + cutover scheduling + DNS switch + health check in one pipeline; rollback pre-built | +3%: Orchestrated pipeline reduces handoff time between replication-complete and cutover-execute. MGN/ASR do the heavy lifting regardless — our value is coordination layer | Cutover windows are business-driven, not tool-driven | Medium | AWS MGN + Gartner
Replatform Execution | 55% | 57% |  | Scripted OS/DB upgrades via SSM/Ansible; pre/post validation manual; separate tooling for each step | Upgrade executor chains SSM scripts + validation in orchestrated workflow; auto-generated pre/post validation checks from discovery baselines | +2%: Auto-generated validation checks from baselines save manual checklist creation. Upgrade scripts themselves are standard SSM/Ansible regardless of tool | DB upgrades (especially Oracle -> Aurora) have unpredictable compatibility issues | Medium | Industry avg
Containerize Execution | 55% | 58% |  | CI/CD pipeline (Jenkins/GitHub Actions) for build-push-deploy; manual smoke testing and config validation | Integrated CI/CD pipeline with automated health checks + canary validation; pre-configured from artifact generation phase | +3%: Pre-configured pipeline from artifact gen phase eliminates manual CI/CD setup. Health checks auto-generated from discovery baselines. Smoke testing still manual | App-specific validation (business logic) cannot be automated | Medium | CNCF 2024
FR Testing (60% effort) | 50% | 53% |  | Manual test case design + Selenium/Cypress execution; test automation frameworks exist but setup is per-project | AI-generated test cases from app behavior analysis + parallel execution framework; reduces test design time but defect triage still manual | +3%: AI test case generation saves 20-30% of test design effort (the other 50% is execution which is already automatable). Defect triage and root cause = human | Business-logic test cases require domain knowledge no AI can replace | Medium | Forrester TEI
NFR Testing (30% effort) | 50% | 52% |  | Manual JMeter/Gatling scripting + result analysis; performance baselines compared manually | Auto-generated load scripts from traffic patterns + AI performance comparison against discovery baselines | +2%: Auto-generated scripts from real traffic patterns more representative than manually designed scenarios. But bottleneck identification and tuning are human tasks | Performance issues often root-cause to architecture, not configuration | Medium | Gartner
Right-Sizing | 70% | 72% |  | AWS Compute Optimizer / Azure Advisor — already highly accurate (80%+ match rate); cloud-native tools are mature here | Unified right-sizing across AWS+Azure+AzLocal in single view; but cloud-native tools already do this well individually | +2%: Marginal — unified view is convenient but cloud-native tools are excellent. Our value is cross-cloud comparison, not better analysis | Honest: AWS Compute Optimizer is hard to beat on AWS-specific sizing | Medium-High | AWS Compute Opt
Monitoring Setup | 55% | 57% |  | Terraform modules for CloudWatch/Azure Monitor + manual Grafana dashboard creation | Pre-built monitoring templates + Grafana integration auto-deployed from discovery metadata; PG&E-specific SLOs still manual | +2%: Pre-built templates from discovery metadata save dashboard creation time. Alert thresholds auto-suggested from baselines. Custom SLOs remain manual | PG&E-specific operational requirements drive custom alerting regardless | Medium | Datadog/Grafana
Vuln Discovery Scan | 65% | 68% |  | Nessus/Qualys scan separately + manual CVSS triage in spreadsheet; separate from migration workflow | Integrated vuln scanning in migration pipeline + CVSS auto-triage + false-positive filtering using migration context (e.g., server being retired = deprioritize) | +3%: Migration-context-aware triage is the differentiator. Generic vuln scanners dont know which servers are being retired vs migrated — our tool does, reducing unnecessary triage | Critical CVEs on NERC CIP systems still need manual human review regardless | Medium-High | Tenable/Qualys
Vuln Remediation Planning | 55% | 58% |  | Manual CVE-to-patch mapping + change request creation in ServiceNow; patch scheduling around change windows | AI-prioritized remediation plan with auto-generated runbooks + change request drafts; migration-aware scheduling (patch before migrate, not after) | +3%: Migration-aware scheduling prevents patch-then-migrate vs migrate-then-patch conflicts. Auto-generated runbooks save 1-2 days per wave planning cycle | CAB approval and change window negotiation are organizational, not tool-solvable | Medium | ServiceNow VR
Vuln Patch Execution | 55% | 57% |  | SSM/Ansible patch automation + manual validation; compliance evidence collected separately | Orchestrated patching with auto-generated compliance evidence trail; NERC CIP audit-ready output | +2%: Auto-generated compliance evidence trail saves manual documentation. But NERC CIP sign-off is still manual regulatory process | Patch rollback scenarios still need human decision-making | Medium | AWS SSM
Vuln Continuous Monitoring | 60% | 62% |  | Scheduled scans + manual ticket creation in JIRA/ServiceNow; periodic reporting | Continuous scanning + auto-ticketing + Grafana vuln posture dashboard with SLA tracking | +2%: Auto-ticketing and dashboard are convenient but not transformational. The real work is remediation follow-up which is manual regardless | Dashboard ≠ remediation. Pretty charts dont fix CVEs | Medium | Industry avg
WEIGHTED AVERAGE | [5 empty] | Concierto Migrate provides ~3-4% incremental improvement over industry standard on average
Honest Summary: Where Concierto Migrate Genuinely Adds Value
STRONG ADVANTAGES (+5-7% over industry): Integration & Multi-Cloud Unification
1. UNIFIED MULTI-CLOUD DISCOVERY: Single scan across AWS+Azure+AzLocal vs running 3 separate tools and merging spreadsheets. For 4273 servers across 3 clouds, this saves 3-5 days of reconciliation.
2. DISCOVERY-TO-IaC PIPELINE: Terraform auto-generated FROM discovery data — no manual translation of inventory into HCL variables. Industry tools have a gap between discovery output and IaC input.
3. DISCOVERY-TO-TCO PIPELINE: TCO auto-generated from actual inventory vs manual AWS/Azure pricing calculator input. Eliminates data-entry errors and multi-cloud comparison spreadsheets.
4. DB REMEDIATION LAYER: Goes beyond SCT reporting — provides AI-suggested fixes for unconverted objects. SCT tells you what failed; our tool suggests how to fix it.
5. MIGRATION-CONTEXT VULN TRIAGE: Generic vuln scanners dont know migration context. Our tool deprioritizes CVEs on servers being retired, prioritizes servers being migrated first.
MODERATE ADVANTAGES (+2-3%): Orchestration & Workflow Automation
6. ORCHESTRATED EXECUTION: Single pipeline for replication -> cutover -> DNS -> validation vs manual handoffs between MGN console, Route53, and monitoring dashboard.
7. REHEARSAL ORCHESTRATION: Automated rehearsal execution + outcome validation vs manual runbook + spreadsheet checklist.
8. AI TEST GENERATION: Test cases auto-generated from app behavior analysis. Saves ~20-30% of test design time. Execution speed is same (Selenium/Cypress).
9. PRE-BUILT MONITORING: Templates auto-deployed from discovery metadata. Saves dashboard creation time but custom PG&E SLOs still manual.
HONEST LIMITATIONS (0-2%): Areas Where Our Tool Doesnt Significantly Outperform
10. COMPLIANCE / NERC CIP: Regulatory compliance is fundamentally manual. Our scanning is marginally faster but the bottleneck (evidence collection, auditor review) is unchanged. +2% max.
11. FRAMEWORK UPGRADES: Code refactoring is a developer skill. Our Upgrade Advisor helps with identification, but actual .NET/Java code changes need developers. +2% max.
12. MIDDLEWARE MIGRATION: Custom plugin compatibility is per-product analysis. Tool can extract configs but cant validate WebLogic-to-Tomcat plugin compatibility automatically.
13. PERFORMANCE BASELINE: Cloud-native monitoring (CloudWatch, Azure Monitor) is already excellent. Our unified view is convenient but doesnt collect metrics faster. 0% delta.
14. RIGHT-SIZING: AWS Compute Optimizer is genuinely best-in-class for AWS. Our value is cross-cloud comparison, not better per-cloud sizing. +2% max.
BOTTOM LINE FOR EXECUTIVES
Concierto Migrate does NOT claim to be 2x faster than industry tools. It provides a consistent 3-7% improvement in high-impact areas
through INTEGRATION (eliminating manual handoffs between 10+ separate tools) rather than making individual activities dramatically faster.
The real value proposition is: ONE PLATFORM replacing AWS Migration Hub + Azure Migrate + SCT + DMA + Terraform CLI + Nessus + JMeter + 5 spreadsheets.
Time saved = less from faster individual tasks, MORE from eliminated handoff/reconciliation overhead between disconnected tools.
Industry Standard Blended Savings: =B29 ¦ Concierto Blended Savings: =C29 ¦ Net Improvement: =D29

## Cost by Cloud
PG&E Migration Cost by Cloud Platform — Concierto Migrate
415 Apps ¦ 4,273 Servers ¦ Discovery COMPLETED ¦ PG&E provides LZ/Networking
Section A: Migration Duration by Cloud
Cloud Platform | Apps | Servers | Traditional Days | AI Factor | AI Days | Days Saved | Savings % | Months Saved
AWS | 107 | 719 | 533 | 39%
Azure | 145 | 852 | 538 | 39%
Azure Local / HyperV | 130 | 2702 | 586 | 39%
TOTAL
Section B: Migration Cost by Cloud (2-Year)
Cloud Platform | AI Days | Avg FTEs | Blended Rate ($) | Y1 Labor ($) | Y2 Labor (13% SS) | Platform License ($) | Tooling & Other ($) | 2-Year Total ($)
AWS (107 apps) | 208 | 4 | 1050 |  |  | 26667 | 20000
Azure (145 apps) | 210 | 5 | 1050 |  |  | 26667 | 20000
Azure Local/HV (130 apps) | 229 | 5 | 1050 |  |  | 26667 | 20000
Contingency (12%)
GRAND TOTAL (2-Year)
Traditional 2-Year (No AI) | [7 empty] | 10174500
NET SAVINGS
Tool: Concierto Migrate
Full multi-cloud coverage. Strong rehost (CloudMach) + modernize